ANALYTICS ENGINEER ROADMAP

52 Weeks from MySQL DBA to Analytics Engineer on Upwork

Snowflake · BigQuery · dbt · Batch ELT · Streaming · SQL & Python

Start: Monday 28 Sep 2026

Finish: Sunday 26 Sep 2027

Pace: about 20 hours per week, alongside your current work

Output: 12 portfolio projects, 2 certifications, a specialized Upwork profile and 3 productized offers

Companion file: Analytics_Engineer_Tracker.xlsx

Contents

1. How this plan works	1

Assumptions	1

Your starting advantages	1

Weekly rhythm (20 hours)	1

2. The six phases	1

3. Milestones and income targets	1

4. Week-by-week plan	1

5. Project briefs	1

P1. Sakila: from MySQL to a star schema	1

P2. Olist marketplace analytics on Snowflake	1

P3. GA4 marketing analytics on BigQuery	1

P4. SaaS revenue metrics (MRR, churn, LTV)	1

P5. NYC Taxi batch pipeline	1

P6. MySQL to Snowflake migration	1

P7. Real-time orders with CDC	1

P8. Large-scale processing with PySpark	1

P9. Warehouse cost audit	1

P10. E-commerce analytics starter kit	1

P11. Redshift port	1

P12. Capstone: modern data platform	1

6. Upwork transition plan	1

Keep your current income	1

Use a specialized profile	1

Bridge offers first	1

Proposal routine	1

Rate ladder	1

7. Portfolio standard	1

Every project README includes	1

Case study (for your Upwork portfolio)	1

8. Learning resources	1

9. Using the tracker	1

# 1. How this plan works

This plan takes you from your current Upwork position (MySQL administration, DevOps and system administration) to analytics engineer profile that can win data warehousing, dbt and ELT jobs. It is built around projects: every phase ends with portfolio pieces you can show clients, and you start bidding on analytics work in week 11, long before the year ends.

## Assumptions

- Time: about 20 hours per week. If you can give more, compress the plan; if a week slips, use the buffer weeks (16, 36, 46) instead of skipping projects.

- Main warehouse: Snowflake, learned in depth. BigQuery is your second warehouse. Redshift is covered at a working level in one project (P11).

- Streaming: covered in Phase 4 (weeks 27–36) through CDC from MySQL, which builds on your DBA experience. Deep streaming work continues in year 2.

- Income: you keep taking DBA/DevOps jobs while you learn. The plan gradually shifts your Upwork work toward analytics.

- Cost: most learning runs free on DuckDB, the BigQuery sandbox and local Docker. Snowflake's free trial is time-limited, so start it in week 7. After it ends, keep a small monthly budget, use extra-small warehouses with auto-suspend, and set a resource monitor so you never get a surprise bill.

## Your starting advantages

You are not starting from zero, and the plan uses that:

- MySQL administration means you already understand schemas, indexes, query plans, binlogs and replication. P1, P6 and P7 are built directly on this.

- DevOps and Linux skills make Docker, Airflow, Airbyte, Kafka and Terraform much easier for you than for most analytics engineers. Many of them cannot deploy their own tools.

- You already have an Upwork account with a job history and reviews. You don't start as an unknown profile, and your first analytics offers can be "bridge" offers such as MySQL-to-Snowflake migration.

## Weekly rhythm (20 hours)

| When | Hours | What |
| --- | --- | --- |
| Sunday to Thursday evenings | 2 h × 5 = 10 h | Learning from the "Learn" column, small exercises |
| Friday | 6 h | Project work from the "Build" column |
| Saturday | 3 h | Project work, README and documentation |
| Saturday | 1 h | Upwork: proposals, profile, follow-ups (from week 11) |

Adjust the days to your own week. The important part is protecting the long project block: projects need several uninterrupted hours.

# 2. The six phases

| Phase | Weeks | Goal | Projects |
| --- | --- | --- | --- |
| 1. Foundations & bridge from DBA | 1–6 | Analytical SQL, dimensional modeling, Python for data and dbt basics. Turn your MySQL strength into your first analytics project. | P1 |
| 2. Warehouses + dbt in depth | 7–16 | Snowflake as your main warehouse, BigQuery as your second, dbt to an intermediate-advanced level, CI and testing. Start bidding on small analytics jobs. | P2, P3 |
| 3. Batch ELT: ingestion & orchestration | 17–26 | Airbyte, Python extractors with dlt, Airflow, cloud storage and Snowpipe. Build full pipelines and a MySQL-to-Snowflake migration. | P4, P5, P6 |
| 4. Streaming & large-scale processing | 27–36 | Kafka, CDC with Debezium from MySQL, loading streams into Snowflake, PySpark and lakehouse table formats. | P7, P8 |
| 5. Client-ready specialization | 37–46 | Cost optimization, observability, a productized e-commerce offer, BI and semantic layer, Redshift, Terraform for data, consulting skills. | P9, P10, P11 |
| 6. Capstone, certification & launch | 47–52 | One full modern data platform as your flagship project, certification exams, portfolio polish and a rate increase. | P12 |

# 3. Milestones and income targets

These targets connect the learning plan to the long-term goal of $5,000 per month. They are checkpoints, not promises: freelance results vary, so review them at each milestone and adjust.

| By week | Portfolio | Upwork (analytics niche) | Rate target |
| --- | --- | --- | --- |
| Week 11 (13 Dec) | P1, P2 | Specialized analytics profile live; 2–3 proposals per week | $25/hr for first niche jobs |
| Week 26 (28 Mar) | P1–P6 | 3–5 reviews in the niche; migration offer in Project Catalog | $25–30/hr |
| Week 36 (6 Jun) | P1–P8 | 1 ongoing client; real-time/CDC on profile | $30–35/hr |
| Week 46 (15 Aug) | P1–P11 | 3 productized offers live; win rate reviewed | $40–45/hr |
| Week 52 (26 Sep) | All 12 + 2 certifications | 1–2 ongoing clients; Top Rated status | $45–50/hr for new clients |
| Year 2 | Deeper streaming, case studies with real results | Retainers; Toptal application once you have the seniority | $50–65/hr → $5,000/month |

# 4. Week-by-week plan

Each row is one week. "Learn" is the study for the week, "Build" is what you produce, and "Upwork" is the platform action. Tick weeks off in the Weekly Plan sheet of the tracker.

Phase 1: Foundations & bridge from DBA  (weeks 1–6)

Analytical SQL, dimensional modeling, Python for data and dbt basics. Turn your MySQL strength into your first analytics project.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 1 28 Sep – 4 Oct 20 h | Advanced analytical SQL I | Window functions (ROW_NUMBER, RANK, LAG/LEAD, running totals), CTEs, QUALIFY, GROUPING SETS/ROLLUP, CASE-based pivots. Install DuckDB and practice locally for free. | Solve 30 analytical SQL exercises on a sample dataset; push to a GitHub repo 'sql-analytics-practice'. | Audit your current profile. List the past DBA/DevOps jobs that support an analytics story (SQL tuning, MySQL, Docker, Linux). |
| Week 2 5 Oct – 11 Oct 20 h | Advanced analytical SQL II | Analytics patterns: cohorts, retention, funnels, sessionization, gaps-and-islands, date spines, deduplication, percentiles. Reading query plans in a columnar engine vs MySQL. | Add 20 pattern exercises with written explanations to the practice repo. | Save 20 real analytics engineer / dbt / Snowflake job posts to a research list. Note tools, budgets and wording. |
| Week 3 12 Oct – 18 Oct 20 h · P1 | Dimensional modeling (Kimball) | Grain, fact types (transaction, periodic snapshot, accumulating), conformed dimensions, surrogate keys, SCD types 1/2, bus matrix, one-big-table vs star schema. | P1 starts: design a bus matrix and star schema for the MySQL Sakila sample database. | Summarize the 20 saved posts: top 10 recurring requirements. Adjust the plan if something big is missing. |
| Week 4 19 Oct – 25 Oct 20 h | Python for data work | pandas or polars basics, requests, API pagination and retries, environment variables and secrets, logging, pytest, project structure with virtual environments. | Python extractor exercise: a public REST API to Parquet files, with tests and logging. | Keep taking DBA/DevOps work for income. No new-niche bids yet. |
| Week 5 26 Oct – 1 Nov 20 h · P1 | dbt fundamentals | dbt-duckdb setup, project structure (staging / intermediate / marts), sources, ref, materializations, generic tests, docs, seeds. Complete the free dbt Fundamentals course. | P1: staging and intermediate models for Sakila in dbt on DuckDB. | Draft a new headline and overview that bridge 'MySQL DBA' to 'data warehouse / analytics'. |
| Week 6 2 Nov – 8 Nov 20 h · P1 | Project 1 delivery | Metabase basics (run in Docker), writing a project README, drawing a simple architecture diagram. | P1 finish: fact and dimension marts, tests, dbt docs, Metabase dashboard, README with business story. | Add P1 to your portfolio. Update your profile with the bridge headline. |

Phase 2: Warehouses + dbt in depth  (weeks 7–16)

Snowflake as your main warehouse, BigQuery as your second, dbt to an intermediate-advanced level, CI and testing. Start bidding on small analytics jobs.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 7 9 Nov – 15 Nov 20 h · P2 | Snowflake architecture | Virtual warehouses, micro-partitions, RBAC and roles, stages, file formats, COPY INTO, time travel, zero-copy cloning, credit usage, resource monitors, auto-suspend. | Start the Snowflake free trial. Load the Olist e-commerce CSVs through a stage with COPY INTO. Script your roles and warehouses. | Take the Snowflake-related Upwork skill tags into your profile once you have used them. |
| Week 8 16 Nov – 22 Nov 20 h · P2 | dbt intermediate | Incremental models (merge strategy, is_incremental), snapshots for SCD2, Jinja and macros, packages (dbt_utils, dbt_expectations), exposures. | P2: staging and intermediate models for Olist on Snowflake. | Read 10 winning-style proposals in the analytics category (profiles of top freelancers) and note their structure. |
| Week 9 23 Nov – 29 Nov 20 h · P2 | Project 2: marts & tests | Designing marts for business questions, naming conventions, test coverage strategy. | P2: fct_orders, fct_order_items, dim_customers, dim_sellers, dim_products, dim_date with tests. | Write 3 proposal templates: dbt fix, SQL optimization, dashboard + model. |
| Week 10 30 Nov – 6 Dec 20 h · P2 | Project 2: metrics & dashboard | Metric definitions (revenue, AOV, delivery SLA, repeat rate), BI tool of choice (Metabase, Looker Studio or Power BI). | P2: dashboard for revenue, delivery performance, seller performance and review score vs delay. Publish dbt docs. | Prepare the specialized profile text: 'Analytics Engineer ¦ Snowflake + dbt'. |
| Week 11 7 Dec – 13 Dec 20 h · P2 | CI/CD for dbt | GitHub Actions for dbt build on pull requests, slim CI with state:modified, separate dev and prod targets, pre-commit and SQLFluff linting. | P2 finish: CI pipeline, README, one-page case study. | Publish the specialized profile. Start 2–3 proposals per week on small dbt/SQL/dashboard jobs. |
| Week 12 14 Dec – 20 Dec 20 h · P3 | BigQuery fundamentals | Storage vs compute, partitioning and clustering, on-demand pricing (bytes scanned), nested and repeated fields (STRUCT, ARRAY, UNNEST), the free sandbox. | Explore the public GA4 sample dataset (bigquery-public-data.ga4_obfuscated_sample_ecommerce). | 3 proposals. Track every one in the Upwork Pipeline sheet. |
| Week 13 21 Dec – 27 Dec 20 h · P3 | Project 3: GA4 modeling | GA4 event schema, flattening event_params, sessionization, channel grouping, funnels. | P3: dbt-bigquery project with sessions, events and funnel models. | 3 proposals. Prefer fixed-price jobs under $300 for fast reviews. |
| Week 14 28 Dec – 3 Jan 20 h · P3 | Project 3 delivery | Looker Studio, cost measurement in BigQuery (bytes scanned before and after partitioning). | P3 finish: Looker Studio dashboard, cost notes, README, case study. | Add P2 and P3 to the portfolio. 3 proposals. |
| Week 15 4 Jan – 10 Jan 20 h | Data quality & dbt testing | Singular and generic tests, dbt unit tests, model contracts, source freshness, intro to the dbt Semantic Layer. | Add unit tests, contracts and freshness checks to P2. | 3–5 proposals. Follow up on any viewed proposals. |
| Week 16 11 Jan – 17 Jan 15 h | Review & buffer | Catch up on anything behind. Review weak spots from the Skills sheet. | Clean GitHub, write a GitHub profile README that links all projects. Mid-phase retrospective. | Review proposal stats: views, replies, interviews. Improve the weakest template. |

Phase 3: Batch ELT: ingestion & orchestration (weeks 17–26)

Airbyte, Python extractors with dlt, Airflow, cloud storage and Snowpipe. Build full pipelines and a MySQL-to-Snowflake migration.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 17 18 Jan – 24 Jan 20 h | Ingestion with Airbyte | Self-hosting Airbyte with Docker, connectors, sync modes (full refresh, incremental append, incremental dedup), CDC concepts. Fivetran concepts and pricing model. | Airbyte sync from MySQL/Postgres into Snowflake. | 3–5 proposals. Include 'Airbyte / ELT setup' jobs where your DevOps skills help. |
| Week 18 25 Jan – 31 Jan 20 h | Custom extractors with dlt | dlt (data load tool): REST sources, pagination, rate limits, incremental cursors, schema evolution, secrets handling. | dlt pipeline from a public API into Snowflake with incremental loading. | 3–5 proposals. |
| Week 19 1 Feb – 7 Feb 20 h · P4 | Project 4: SaaS data ingestion | Stripe data model (customers, subscriptions, invoices), CRM data basics. | P4: generate Stripe test-mode data with a script, plus CRM and targets data; load all into Snowflake with dlt/Airbyte. | 3–5 proposals. |
| Week 20 8 Feb – 14 Feb 20 h · P4 | Project 4: SaaS metrics | MRR, churn, expansion, contraction, cohort retention, LTV definitions. | P4 finish: dbt metric models, dashboard, README, case study. | Add P4 to portfolio. 3–5 proposals. |
| Week 21 15 Feb – 21 Feb 20 h | Orchestration with Airflow | DAGs, operators, TaskFlow API, scheduling, retries, connections, Docker Compose deployment, Astronomer Cosmos for running dbt. Look at Dagster at a concept level. | Airflow running P4 end to end on a daily schedule. | 3–5 proposals. Airflow setup jobs are a good bridge from DevOps. |
| Week 22 22 Feb – 28 Feb 20 h | Cloud storage & loading patterns | S3 or GCS, IAM basics, external stages, Snowpipe auto-ingest, Parquet, partitioned file layouts. | S3 bucket plus a Snowpipe auto-ingest demo. | 3–5 proposals. |
| Week 23 1 Mar – 7 Mar 20 h · P5 | Project 5: NYC Taxi batch pipeline | Idempotent loads, backfills, incremental models on large tables. | P5: monthly NYC TLC Parquet files → S3 → Snowflake → dbt incremental models, scheduled with Airflow. | 3–5 proposals. |
| Week 24 8 Mar – 14 Mar 20 h · P5 | Project 5 delivery | Alerting on failure (Slack or email), rerun safety, performance notes. | P5 finish: backfill of 12+ months, alerts, dashboard, README, case study. | Add P5 to portfolio. 3–5 proposals. |
| Week 25 15 Mar – 21 Mar 20 h · P6 | Project 6: MySQL → Snowflake migration | Schema and data type mapping, initial load strategies, incremental sync, reconciliation (row counts, checksums, aggregates). | P6: migrate a realistic MySQL database (e.g., Sakila scaled up or the MySQL employees sample) into Snowflake. | Draft a fixed-price offer: 'MySQL to Snowflake/BigQuery migration'. It uses your existing reviews. |
| Week 26 22 Mar – 28 Mar 20 h · P6 | Project 6 delivery + mid-year review | Cutover planning, runbooks, validation reports. | P6 finish: cutover runbook, validation report, cost comparison, case study. | Publish the migration offer in the Project Catalog. Mid-year review of rate and win rate. |

Phase 4: Streaming & large-scale processing (weeks 27–36)

Kafka, CDC with Debezium from MySQL, loading streams into Snowflake, PySpark and lakehouse table formats.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 27 29 Mar – 4 Apr 20 h | Kafka fundamentals | Topics, partitions, consumer groups, offsets, delivery semantics. Run Kafka or Redpanda in Docker. Python producers and consumers. | Producer/consumer exercise with an order-event generator. | 3–5 proposals. Keep 1 active client if possible. |
| Week 28 5 Apr – 11 Apr 20 h · P7 | CDC with Debezium | MySQL binlog configuration (your strength), Kafka Connect, Debezium MySQL connector, schema registry basics. | Debezium capturing inserts, updates and deletes from MySQL into Kafka topics. | 3–5 proposals. |
| Week 29 12 Apr – 18 Apr 20 h · P7 | Streams into the warehouse | Snowflake Kafka connector and Snowpipe Streaming, Dynamic Tables, late-arriving data, deduplication. BigQuery streaming at a concept level. | Kafka topics landing in Snowflake with Dynamic Tables on top. | 3–5 proposals. |
| Week 30 19 Apr – 25 Apr 20 h · P7 | Project 7: real-time CDC build | End-to-end latency, ordering, handling deletes. | P7: order-app simulator in MySQL → Debezium → Kafka → Snowflake → Dynamic Tables/dbt. | 3–5 proposals. |
| Week 31 26 Apr – 2 May 20 h · P7 | Project 7 delivery | Measuring latency, failure and replay testing. | P7 finish: near-real-time dashboard, latency measurements, failure test notes, README, case study. | Add P7 to portfolio. Add 'real-time / CDC' to your profile. |
| Week 32 3 May – 9 May 20 h · P8 | Spark fundamentals | PySpark DataFrames, partitions, shuffles, join strategies, caching, file formats. Use Databricks Free Edition or local Spark. | PySpark exercises on a multi-GB dataset. | 3–5 proposals. |
| Week 33 10 May – 16 May 20 h · P8 | Project 8: large-scale batch | Partitioning output, small-files problem, writing to Delta/Iceberg tables. | P8: process multiple years of NYC taxi data with PySpark into partitioned lakehouse tables, then load aggregates into the warehouse. | 3–5 proposals. |
| Week 34 17 May – 23 May 20 h · P8 | Project 8 delivery + Structured Streaming | Spark Structured Streaming basics, reading from Kafka. | P8 finish, plus a small Structured Streaming job reading P7's Kafka topic. README, case study. | Add P8 to portfolio. |
| Week 35 24 May – 30 May 15 h | Lakehouse & open table formats | Apache Iceberg and Delta Lake, Iceberg tables in Snowflake and BigQuery, when a lakehouse makes sense vs a warehouse. | Write a comparison article (LinkedIn or blog) as a portfolio piece. | Share the article on LinkedIn. 3–5 proposals. |
| Week 36 31 May – 6 Jun 15 h | Review & buffer | Catch up. Start SnowPro Core study (30 min/day from now). | Retrospective. Update the Skills sheet and GitHub profile. | Review rate: move to $30–35/hr if you have 3+ good reviews in the niche. |

Phase 5: Client-ready specialization (weeks 37–46)

Cost optimization, observability, a productized e-commerce offer, BI and semantic layer, Redshift, Terraform for data, consulting skills.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 37 7 Jun – 13 Jun 20 h · P9 | Warehouse cost & performance | Snowflake query profile, warehouse sizing, clustering keys, caching, resource monitors. BigQuery bytes-scanned optimization and slots. | Cost baseline measurements on P5. | 3–5 proposals. Target 'reduce Snowflake/BigQuery cost' jobs. |
| Week 38 14 Jun – 20 Jun 20 h · P9 | Project 9: cost audit | Writing an audit report for a non-technical client. | P9: deliberately inefficient setup → measure → optimize → before/after report with credits saved. | Turn P9 into a fixed-price 'warehouse cost audit' offer. |
| Week 39 21 Jun – 27 Jun 20 h | Data observability | Elementary (dbt package), freshness and volume anomalies, alerting. Great Expectations at a concept level. | Add Elementary monitoring to P2 and P5. | 3–5 proposals. |
| Week 40 28 Jun – 4 Jul 20 h · P10 | Project 10: e-commerce starter kit | Shopify data model (orders, line items, customers, refunds). Create a free Shopify development store for test data. | P10: reusable dbt project template for Shopify-style stores, standard marts, dashboard template. | 3–5 proposals. |
| Week 41 5 Jul – 11 Jul 20 h · P10 | Project 10: productize it | Packaging a service: scope, tiers, timelines. | P10 finish: README, setup guide, demo video. | Publish a Project Catalog offer with 3 fixed-price tiers based on P10. |
| Week 42 12 Jul – 18 Jul 20 h | BI & semantic layer | Power BI data modeling basics, Looker/LookML concepts, dbt Semantic Layer, writing a metrics definitions document with stakeholders. | Metrics definitions doc and semantic models for P2. | 3–5 proposals. |
| Week 43 19 Jul – 25 Jul 15 h · P11 | Project 11: Redshift port | Redshift Serverless, distribution and sort keys, COPY from S3, differences from Snowflake. | P11: port P2 to Redshift Serverless (use free trial credits) and document the differences. | Add Redshift to profile skills with P11 as proof. |
| Week 44 26 Jul – 1 Aug 20 h | Infrastructure as code for data | Terraform Snowflake provider, dev/prod environments, secrets, repeatable setup (your DevOps edge). | Terraform module that creates databases, warehouses, roles and users for a new client. | 3–5 proposals. |
| Week 45 2 Aug – 8 Aug 15 h | Consulting skills | Discovery calls, scoping, estimating, statements of work, handover documentation. | Discovery-call checklist, estimate template, handover template. | Refresh all proposal templates using what worked so far. |
| Week 46 9 Aug – 15 Aug 15 h | Review & exam prep | SnowPro Core practice exams. dbt Analytics Engineering Certification study guide. | Retrospective. Book exam dates for week 51. | Rate review: move to $40–45/hr if win rate holds. |

Phase 6: Capstone, certification & launch (weeks 47–52)

One full modern data platform as your flagship project, certification exams, portfolio polish and a rate increase.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 47 16 Aug – 22 Aug 20 h · P12 | Capstone design | Architecture decision records, requirements writing. | P12: requirements, architecture diagram, Terraform setup of all environments. | 3–5 proposals. Keep active clients happy first. |
| Week 48 23 Aug – 29 Aug 20 h · P12 | Capstone build I | — | P12: batch ingestion (dlt/Airbyte) plus CDC stream; dbt staging and marts. | 3–5 proposals. |
| Week 49 30 Aug – 5 Sep 20 h · P12 | Capstone build II | — | P12: orchestration, CI/CD, Elementary monitoring, dashboard. | 3–5 proposals. |
| Week 50 6 Sep – 12 Sep 20 h · P12 | Capstone delivery | Recording a clear walkthrough video. | P12 finish: runbook, docs, 5-minute walkthrough video, case study. | Make P12 the first item in your portfolio. |
| Week 51 13 Sep – 19 Sep 15 h | Certification week | Final review. | Take SnowPro Core and the dbt Analytics Engineering exam. | Add certifications to your profile. |
| Week 52 20 Sep – 26 Sep 15 h | Launch & year-2 plan | — | Portfolio polish, update every case study with results. Year retrospective. Write the year-2 plan. | Raise your rate to $45–50/hr for new clients. Set year-2 targets. |

# 5. Project briefs

Twelve projects, each built around a business story. Clients hire for outcomes, so every README and case study should open with the problem, not the tools.

## P1. Sakila: from MySQL to a star schema

| Weeks | 3–6 |
| --- | --- |
| Business story | A DVD rental chain runs everything on MySQL and can't answer basic questions: which films earn most, which stores perform best, which customers churn. |
| Data | MySQL Sakila sample database |
| Stack | MySQL, DuckDB, dbt-duckdb, Metabase (Docker) |
| Deliverables | Bus matrix, star schema (fct_rentals, fct_payments, dims), dbt tests and docs, Metabase dashboard, README |
| Done when | dbt build passes with tests on every primary key; dashboard answers 5 business questions |
| Upwork jobs it proves | Data modeling, reporting on top of MySQL, 'turn my database into dashboards' jobs |

## P2. Olist marketplace analytics on Snowflake

| Weeks | 7–11, 15 |
| --- | --- |
| Business story | A marketplace wants one trusted source for revenue, delivery performance and seller quality. |
| Data | Brazilian E-Commerce Public Dataset by Olist (Kaggle) |
| Stack | Snowflake, dbt Core, GitHub Actions, SQLFluff, Metabase/Power BI |
| Deliverables | Staged, intermediate and mart models; snapshots; unit tests and contracts; CI; dashboard; case study |
| Done when | CI runs on every pull request; dashboard shows revenue, AOV, delivery SLA, seller scores |
| Upwork jobs it proves | Core Snowflake + dbt jobs, the most common analytics engineer post |

## P3. GA4 marketing analytics on BigQuery

| Weeks | 12–14 |
| --- | --- |
| Business story | An online store wants to understand sessions, funnels and which channels bring buyers. |
| Data | bigquery-public-data.ga4_obfuscated_sample_ecommerce |
| Stack | BigQuery, dbt-bigquery, Looker Studio |
| Deliverables | Session and funnel models, channel grouping, dashboard, cost notes on partitioning |
| Done when | Funnel from session to purchase by channel; documented bytes-scanned savings |
| Upwork jobs it proves | GA4/BigQuery jobs, very common with marketing agencies and small stores |

## P4. SaaS revenue metrics (MRR, churn, LTV)

| Weeks | 19–20 |
| --- | --- |
| Business story | A SaaS founder needs MRR, churn and cohort retention without paying for an expensive tool. |
| Data | Stripe test-mode data generated by script, CRM data, targets sheet |
| Stack | Python, dlt, Airbyte, Snowflake, dbt, Airflow (added week 21) |
| Deliverables | Ingestion pipelines, MRR movement and cohort models, dashboard, case study |
| Done when | MRR bridge (new, expansion, contraction, churn) reconciles to raw invoices |
| Upwork jobs it proves | Stripe/SaaS metrics jobs, multi-source ELT |

## P5. NYC Taxi batch pipeline

| Weeks | 23–24 |
| --- | --- |
| Business story | A city operations team needs monthly trip, revenue and zone metrics that refresh automatically. |
| Data | NYC TLC Trip Record Data (monthly Parquet files) |
| Stack | S3, Snowpipe/COPY INTO, Snowflake, dbt incremental, Airflow, Slack/email alerts |
| Deliverables | Scheduled pipeline, 12+ months backfill, alerts, dashboard, case study |
| Done when | Reruns are idempotent; a failed run sends an alert; backfill works by month |
| Upwork jobs it proves | Production batch ELT, orchestration, larger data volumes |

## P6. MySQL to Snowflake migration

| Weeks | 25–26 |
| --- | --- |
| Business story | A company outgrew MySQL reporting and wants to move analytics to Snowflake without losing data. |
| Data | MySQL employees sample database or a scaled-up Sakila |
| Stack | MySQL, Airbyte or dlt, Snowflake, Python reconciliation scripts |
| Deliverables | Type mapping, initial and incremental loads, reconciliation report, cutover runbook, cost comparison |
| Done when | Row counts and checksums match for every table; runbook tested once end to end |
| Upwork jobs it proves | Migration jobs that combine your DBA reviews with the new niche |

## P7. Real-time orders with CDC

| Weeks | 28–31 |
| --- | --- |
| Business story | An operations team wants order status on a dashboard within a minute, not the next morning. |
| Data | Order-app simulator writing to MySQL |
| Stack | MySQL binlog, Debezium, Kafka/Redpanda, Snowflake Kafka connector, Dynamic Tables, dbt |
| Deliverables | CDC pipeline, near-real-time dashboard, latency measurements, failure/replay notes |
| Done when | Inserts, updates and deletes appear in Snowflake within target latency; replay after failure works |
| Upwork jobs it proves | Streaming and CDC jobs, higher-rate work |

## P8. Large-scale processing with PySpark

| Weeks | 32–34 |
| --- | --- |
| Business story | An analyst team needs multi-year trends from data too large to process comfortably in pandas. |
| Data | Several years of NYC TLC data (or GitHub Archive) |
| Stack | PySpark, Databricks Free Edition or local Spark, Delta/Iceberg, Structured Streaming |
| Deliverables | Partitioned lakehouse tables, aggregates loaded to the warehouse, small streaming job, case study |
| Done when | Job runs on the full dataset with documented partitioning and performance choices |
| Upwork jobs it proves | Spark / big data batch jobs |

## P9. Warehouse cost audit

| Weeks | 37–38 |
| --- | --- |
| Business story | A client's Snowflake bill doubled and nobody knows why. |
| Data | Your P5 environment, deliberately misconfigured |
| Stack | Snowflake query history, query profile, resource monitors, dbt |
| Deliverables | Audit report with before/after credits, list of fixes, monitoring setup |
| Done when | Measured cost reduction with evidence for each change |
| Upwork jobs it proves | Cost optimization jobs, a strong fixed-price offer |

## P10. E-commerce analytics starter kit

| Weeks | 40–41 |
| --- | --- |
| Business story | Small online stores need standard reporting fast, without a custom project each time. |
| Data | Shopify development store (free) with test orders |
| Stack | Shopify API, dlt, Snowflake or BigQuery, dbt template, dashboard template |
| Deliverables | Reusable dbt project, setup guide, demo video, Project Catalog offer |
| Done when | A new store can be set up from the template in one day |
| Upwork jobs it proves | Productized service you can sell repeatedly |

## P11. Redshift port

| Weeks | 43 |
| --- | --- |
| Business story | Show you can deliver on AWS-native warehouses when a client already uses Redshift. |
| Data | P2 Olist models |
| Stack | Redshift Serverless, S3, dbt-redshift |
| Deliverables | Working port of P2, notes on differences (dist/sort keys, COPY, SQL dialect) |
| Done when | dbt build passes on Redshift with the same tests as P2 |
| Upwork jobs it proves | Redshift jobs, multi-warehouse flexibility |

## P12. Capstone: modern data platform

| Weeks | 47–50 |
| --- | --- |
| Business story | A growing company needs a complete, maintainable data platform built from scratch. |
| Data | Combine sources from P4, P7 and P10 |
| Stack | Terraform, Snowflake, dlt/Airbyte, Debezium/Kafka, dbt, Airflow, GitHub Actions, Elementary, BI tool |
| Deliverables | Architecture diagram, IaC, batch + streaming ingestion, dbt layers, CI/CD, monitoring, dashboard, runbook, 5-min video |
| Done when | Someone else could run it from your README; video explains business value in plain words |
| Upwork jobs it proves | Senior, end-to-end work that justifies $45–60/hr |

# 6. Upwork transition plan

## Keep your current income

Do not remove your DBA and DevOps work from Upwork. Those reviews are proof that you deliver. Keep taking those jobs for income until analytics work replaces them.

## Use a specialized profile

Upwork lets you add specialized profiles next to your general one. In week 11 create one titled along the lines of "Analytics Engineer | Snowflake, dbt, BigQuery" and attach only analytics projects to it. Your general profile keeps the DBA/DevOps story.

## Bridge offers first

Your fastest analytics wins will come from jobs that mix your old and new skills. Look for:

- MySQL or Postgres to Snowflake/BigQuery migrations (P6)

- Setting up Airflow, Airbyte or dbt on Docker or a cloud VM (DevOps + data)

- Slow SQL or slow dashboards that need query tuning

- CDC from MySQL into a warehouse (P7)

- Warehouse cost reduction (P9)

## Proposal routine

- Send 2–3 proposals per week from week 11, rising to 3–5 from week 15.

- Prefer small fixed-price jobs early. Five good reviews matter more than one big contract at this stage.

- Open with the client's problem and a short plan. Link the one project that matches their job, not all twelve.

- Log every proposal in the tracker's Upwork Pipeline sheet. Every four weeks, check which templates get replies.

## Rate ladder

Raise your rate for new clients every 2–3 successful contracts. Keep existing clients at their rate, or raise it with notice. Suggested steps: $25 → $30 → $35 → $40–45 → $45–50 by week 52, then $50–65 in year 2.

# 7. Portfolio standard

## Every project README includes

- The business problem in two or three plain sentences

- An architecture diagram (draw.io or Excalidraw is fine)

- The stack and why each tool was chosen

- The data model: a lineage graph screenshot from dbt docs

- Screenshots of the dashboard

- How to run it: setup steps someone else can follow

- What you would do next with more time

## Case study (for your Upwork portfolio)

Keep it to one page: Problem → Approach → Result → Tools. Use numbers wherever possible, such as "cut query time from 40 s to 3 s" or "reduced monthly credits by 35%". Measure these during the project so you have them later.

# 8. Learning resources

Prefer official docs and hands-on courses. Check that course and exam details are current before you start them.

| Topic | Resource |
| --- | --- |
| dbt | dbt Learn free courses (Fundamentals, Jinja & macros, advanced materializations); dbt Developer docs |
| Snowflake | Snowflake documentation and Snowflake Quickstarts; SnowPro Core study guide |
| BigQuery | Google Cloud BigQuery documentation; BigQuery sandbox; GA4 BigQuery export schema docs |
| Modeling | The Data Warehouse Toolkit (Kimball & Ross, 3rd edition) |
| Data engineering overall | Fundamentals of Data Engineering (Reis & Housley); DataTalksClub Data Engineering Zoomcamp (free, on GitHub) |
| Ingestion | dlt (dlthub) docs; Airbyte docs |
| Orchestration | Apache Airflow docs; Astronomer Cosmos docs for dbt in Airflow |
| Streaming & CDC | Kafka documentation; Debezium MySQL connector docs; Snowflake Kafka connector docs |
| Spark | Apache Spark PySpark docs; Databricks Free Edition |
| Observability | Elementary (dbt package) docs |
| Datasets | MySQL Sakila and employees samples; Olist Brazilian E-Commerce (Kaggle); BigQuery GA4 public sample; NYC TLC Trip Record Data; Stripe test mode; Shopify development stores |

# 9. Using the tracker

The Excel tracker follows this document week by week. Its sheets:

- Dashboard: overall progress, hours, projects finished and Upwork numbers, all calculated automatically. Change the start date here and every week's dates update.

- Weekly Plan: all 52 weeks. Fill in actual hours, status, a confidence score (1–5) and notes each Sunday.

- Projects: the 12 projects with status, GitHub link, and whether the case study and Upwork portfolio item are done.

- Skills: rate yourself 1–5 each month and compare against the target level.

- Upwork Pipeline: one row per proposal: Connects, rate, whether it was viewed, interviewed and hired, and contract value.

- Monthly Review: monthly totals pulled from the other sheets plus space for what worked and what to change.

The one rule: finish projects, even imperfectly. Twelve finished, documented projects will win more work than twenty half-built ones.