ANALYTICS ENGINEER ROADMAP

52 Weeks from MySQL DBA to Analytics Engineer on Upwork

Snowflake · BigQuery · dbt · AWS · Google Cloud · Batch ELT · Streaming

Start: Monday 28 Sep 2026

Finish: Sunday 26 Sep 2027

Pace: about 20 hours per week, alongside your current work

Output: 12 portfolio projects (deployed on AWS and Google Cloud), 3 certifications, a specialized Upwork profile and 3 productized offers

Companion file: Analytics_Engineer_Tracker.xlsx

Contents

1. How this plan works	3

Assumptions	3

Your starting advantages	3

Cloud track: AWS first, Google Cloud second	3

Weekly rhythm (20 hours)	4

2. The six phases	4

3. Milestones and income targets	5

4. Week-by-week plan	6

5. Project briefs	13

P1. Sakila: from MySQL to a star schema	13

P2. Olist marketplace analytics on Snowflake	13

P3. GA4 marketing analytics on BigQuery (Google Cloud)	14

P4. SaaS revenue metrics (MRR, churn, LTV)	14

P5. NYC Taxi pipeline deployed on AWS	14

P6. MySQL to Snowflake migration	15

P7. Real-time orders with CDC	15

P8. Serverless lakehouse on AWS (Glue, Athena, Iceberg)	15

P9. Warehouse cost audit	16

P10. E-commerce analytics starter kit	16

P11. Redshift on AWS	16

P12. Capstone: modern data platform on AWS	17

6. Upwork transition plan	17

Keep your current income	17

Use a specialized profile	17

Bridge offers first	17

Proposal routine	17

Rate ladder	18

7. Portfolio standard	18

Every project README includes	18

Case study (for your Upwork portfolio)	18

8. Learning resources	18

9. Using the tracker	19

# 1. How this plan works

This plan takes you from your current Upwork position (MySQL administration, DevOps and system administration) to an analytics engineer profile that can win data warehousing, dbt and ELT jobs. It is built around projects: every phase ends with portfolio pieces you can show clients, and you start bidding on analytics work in week 11, long before the year ends.

## Assumptions

- Time: about 20 hours per week. If you can give more, compress the plan; if a week slips, use the buffer weeks (16 and 36) instead of skipping projects.

- Main warehouse: Snowflake, learned in depth. BigQuery is your second warehouse. Redshift is covered at a working level in one project (P11).

- Streaming: covered in Phase 4 (weeks 27–36) through CDC from MySQL, which builds on your DBA experience. Deep streaming work continues in year 2.

- Cloud: AWS is your main cloud and Google Cloud your second. Azure is left out on purpose: its data work centers on Microsoft tools (Data Factory, Fabric, Power BI, SQL Server) and would be a separate niche.

- Income: you keep taking DBA/DevOps jobs while you learn. The plan gradually shifts your Upwork work toward analytics.

- Cost: early learning runs free on DuckDB, the BigQuery sandbox and local Docker. Snowflake, AWS and Google Cloud all give time-limited trial credits, so start each when its phase begins. Set a billing alarm on every account on day one, use the smallest sizes, and tear environments down with terraform destroy when you are not using them. Plan for a small monthly cloud budget after the trials end.

## Your starting advantages

You are not starting from zero, and the plan uses that:

- MySQL administration means you already understand schemas, indexes, query plans, binlogs and replication. P1, P6 and P7 are built directly on this.

- DevOps and Linux skills make Docker, Airflow, Airbyte, Kafka and Terraform much easier for you than for most analytics engineers. Many of them cannot deploy their own tools.

- Your AWS Cloud Practitioner certificate and Solutions Architect study mean week 22 is about applying AWS to data, not learning cloud from scratch. You have also used Google Cloud before.

- You already have an Upwork account with a job history and reviews. You don't start as an unknown profile, and your first analytics offers can be "bridge" offers such as MySQL-to-Snowflake migration.

## Cloud track: AWS first, Google Cloud second

Clients host their data in their own cloud account, and a big part of what they pay for is getting pipelines running there securely. So the projects move from your laptop to the cloud as the plan goes on:

| Weeks | Cloud work | Project |
| --- | --- | --- |
| 7 | Billing alarms on day one; Snowflake resource monitors | P2 |
| 12–14 | Google Cloud: service accounts, Cloud Storage, dbt as a Cloud Run job on Cloud Scheduler, Secret Manager | P3 |
| 17 | Airbyte self-hosted on EC2 | — |
| 22 | AWS for data: IAM, S3, VPC, Secrets Manager, Lambda, ECS Fargate, CloudWatch, SNS, all with Terraform | — |
| 23–24 | Full pipeline deployed on AWS: S3, Snowpipe via SQS, Airflow on ECS/EC2 (MWAA as a short demo) | P5 |
| 25–26 | Source database on Amazon RDS for MySQL | P6 |
| 29 | Amazon MSK and Kinesis at a concept level | P7 |
| 32–34 | Serverless lakehouse: Glue PySpark jobs, Iceberg on S3, Athena, Step Functions | P8 |
| 43 | Redshift Serverless and Redshift Spectrum | P11 |
| 44 | GitHub Actions deploying to AWS with OIDC (no stored keys) | — |
| 36–46 | AWS Certified Data Engineer – Associate study, exam in week 46 | — |
| 47–50 | Capstone platform deployed on AWS with Terraform | P12 |

Airflow on Amazon MWAA costs noticeably more than running it yourself on ECS or EC2, even at the smallest size. Deploy MWAA once to show you can, record it, then destroy it.

## Weekly rhythm (20 hours)

| When | Hours | What |
| --- | --- | --- |
| Sunday to Thursday evenings | 2 h × 5 = 10 h | Learning from the "Learn" column, small exercises |
| Friday | 6 h | Project work from the "Build" column |
| Saturday | 3 h | Project work, README and documentation |
| Saturday | 1 h | Upwork: proposals, profile, follow-ups (from week 11) |

Adjust the days to your own week. The important part is protecting the long project block: projects need several uninterrupted hours.

# 2. The six phases

| Phase | Weeks | Goal | Projects |
| --- | --- | --- | --- |
| 1. Foundations & bridge from DBA | 1–6 | Analytical SQL, dimensional modeling, Python for data and dbt basics. Turn your MySQL strength into your first analytics project. | P1 |
| 2. Warehouses + dbt in depth | 7–16 | Snowflake as your main warehouse, BigQuery as your second (deployed on Google Cloud), dbt to an intermediate-advanced level, CI and testing. Start bidding on small analytics jobs. | P2, P3 |
| 3. Batch ELT deployed on AWS | 17–26 | AWS for data (IAM, S3, networking, secrets, compute) with Terraform, Airbyte and dlt ingestion, Airflow, Snowpipe. Pipelines run in the cloud, not on your laptop. | P4, P5, P6 |
| 4. Streaming & AWS lakehouse | 27–36 | Kafka and CDC from MySQL into Snowflake, then a serverless lakehouse on AWS with Glue (PySpark), Athena and Iceberg. Start AWS Data Engineer certification study. | P7, P8 |
| 5. Client-ready specialization | 37–46 | Cost optimization, observability, a productized e-commerce offer, BI and semantic layer, Redshift, secure CI/CD to AWS, consulting skills, AWS certification. | P9, P10, P11 |
| 6. Capstone, certification & launch | 47–52 | One full modern data platform deployed on AWS with Terraform as your flagship project, Snowflake and dbt exams, portfolio polish and a rate increase. | P12 |

# 3. Milestones and income targets

These targets connect the learning plan to the long-term goal of $5,000 per month. They are checkpoints, not promises: freelance results vary, so review them at each milestone and adjust.

| By week | Portfolio | Upwork (analytics niche) | Rate target |
| --- | --- | --- | --- |
| Week 11 (13 Dec) | P1, P2 | Specialized analytics profile live; 2–3 proposals per week | $25/hr for first niche jobs |
| Week 26 (28 Mar) | P1–P6 | 3–5 reviews in the niche; migration offer in Project Catalog | $25–30/hr |
| Week 36 (6 Jun) | P1–P8 | 1 ongoing client; real-time/CDC on profile | $30–35/hr |
| Week 46 (15 Aug) | P1–P11 + AWS Data Engineer certificate | 3 productized offers live; win rate reviewed | $40–45/hr |
| Week 52 (26 Sep) | All 12 + SnowPro Core and dbt certificates | 1–2 ongoing clients; Top Rated status | $45–50/hr for new clients |
| Year 2 | Deeper streaming, case studies with real results | Retainers; Toptal application once you have the seniority; optionally finish AWS Solutions Architect – Associate | $50–65/hr → $5,000/month |

# 4. Week-by-week plan

Each row is one week. "Learn" is the study for the week, "Build" is what you produce, and "Upwork" is the platform action. Tick weeks off in the Weekly Plan sheet of the tracker.

Phase 1: Foundations & bridge from DBA  (weeks 1–6)

Analytical SQL, dimensional modeling, Python for data and dbt basics. Turn your MySQL strength into your first analytics project.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 1 28 Sep – 4 Oct 20 h | Advanced analytical SQL I | Window functions (ROW_NUMBER, RANK, LAG/LEAD, running totals), CTEs, QUALIFY, GROUPING SETS/ROLLUP, CASE-based pivots. Install DuckDB and practice locally for free. | Solve 30 analytical SQL exercises on a sample dataset; push to a GitHub repo 'sql-analytics-practice'. | Audit your current profile. List the past DBA/DevOps jobs that support an analytics story (SQL tuning, MySQL, Docker, Linux). |
| Week 2 5 Oct – 11 Oct 20 h | Advanced analytical SQL II | Analytics patterns: cohorts, retention, funnels, sessionization, gaps-and-islands, date spines, deduplication, percentiles. Reading query plans in a columnar engine vs MySQL. | Add 20 pattern exercises with written explanations to the practice repo. | Save 20 real analytics engineer / dbt / Snowflake job posts to a research list. Note tools, budgets and wording. |
| Week 3 12 Oct – 18 Oct 20 h · P1 | Dimensional modeling (Kimball) | Grain, fact types (transaction, periodic snapshot, accumulating), conformed dimensions, surrogate keys, SCD types 1/2, bus matrix, one-big-table vs star schema. | P1 starts: design a bus matrix and star schema for the MySQL Sakila sample database. | Summarize the 20 saved posts: top 10 recurring requirements. Adjust the plan if something big is missing. |
| Week 4 19 Oct – 25 Oct 20 h | Python for data work | pandas or polars basics, requests, API pagination and retries, environment variables and secrets, logging, pytest, project structure with virtual environments. | Python extractor exercise: a public REST API to Parquet files, with tests and logging. | Keep taking DBA/DevOps work for income. No new-niche bids yet. |
| Week 5 26 Oct – 1 Nov 20 h · P1 | dbt fundamentals | dbt-duckdb setup, project structure (staging / intermediate / marts), sources, ref, materializations, generic tests, docs, seeds. Complete the free dbt Fundamentals course. | P1: staging and intermediate models for Sakila in dbt on DuckDB. | Draft a new headline and overview that bridge 'MySQL DBA' to 'data warehouse / analytics'. |
| Week 6 2 Nov – 8 Nov 20 h · P1 | Project 1 delivery | Metabase basics (run in Docker), writing a project README, drawing a simple architecture diagram. | P1 finish: fact and dimension marts, tests, dbt docs, Metabase dashboard, README with business story. | Add P1 to your portfolio. Update your profile with the bridge headline. |

Phase 2: Warehouses + dbt in depth  (weeks 7–16)

Snowflake as your main warehouse, BigQuery as your second (deployed on Google Cloud), dbt to an intermediate-advanced level, CI and testing. Start bidding on small analytics jobs.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 7 9 Nov – 15 Nov 20 h · P2 | Snowflake architecture | Virtual warehouses, micro-partitions, RBAC and roles, stages, file formats, COPY INTO, time travel, zero-copy cloning, credit usage, resource monitors, auto-suspend. | Start the Snowflake free trial. On day one set Snowflake resource monitors and an AWS Budgets alarm on your AWS account. Load the Olist CSVs through a stage with COPY INTO. Script your roles and warehouses. | Take the Snowflake-related Upwork skill tags into your profile once you have used them. |
| Week 8 16 Nov – 22 Nov 20 h · P2 | dbt intermediate | Incremental models (merge strategy, is_incremental), snapshots for SCD2, Jinja and macros, packages (dbt_utils, dbt_expectations), exposures. | P2: staging and intermediate models for Olist on Snowflake. | Read 10 winning-style proposals in the analytics category (profiles of top freelancers) and note their structure. |
| Week 9 23 Nov – 29 Nov 20 h · P2 | Project 2: marts & tests | Designing marts for business questions, naming conventions, test coverage strategy. | P2: fct_orders, fct_order_items, dim_customers, dim_sellers, dim_products, dim_date with tests. | Write 3 proposal templates: dbt fix, SQL optimization, dashboard + model. |
| Week 10 30 Nov – 6 Dec 20 h · P2 | Project 2: metrics & dashboard | Metric definitions (revenue, AOV, delivery SLA, repeat rate), BI tool of choice (Metabase, Looker Studio or Power BI). | P2: dashboard for revenue, delivery performance, seller performance and review score vs delay. Publish dbt docs. | Prepare the specialized profile text: 'Analytics Engineer ¦ Snowflake + dbt'. |
| Week 11 7 Dec – 13 Dec 20 h · P2 | CI/CD for dbt | GitHub Actions for dbt build on pull requests, slim CI with state:modified, separate dev and prod targets, pre-commit and SQLFluff linting. | P2 finish: CI pipeline, README, one-page case study. | Publish the specialized profile. Start 2–3 proposals per week on small dbt/SQL/dashboard jobs. |
| Week 12 14 Dec – 20 Dec 20 h · P3 | BigQuery fundamentals | Storage vs compute, partitioning and clustering, on-demand pricing (bytes scanned), nested fields (STRUCT, ARRAY, UNNEST), the free sandbox. GCP basics: projects, IAM, service accounts, Cloud Storage, billing budgets. | Explore the public GA4 sample dataset (bigquery-public-data.ga4_obfuscated_sample_ecommerce). | 3 proposals. Track every one in the Upwork Pipeline sheet. |
| Week 13 21 Dec – 27 Dec 20 h · P3 | Project 3: GA4 modeling | GA4 event schema, flattening event_params, sessionization, channel grouping, funnels. | P3: dbt-bigquery project with sessions, events and funnel models. | 3 proposals. Prefer fixed-price jobs under $300 for fast reviews. |
| Week 14 28 Dec – 3 Jan 20 h · P3 | Project 3 delivery on Google Cloud | Cloud Run jobs, Cloud Scheduler, Secret Manager, Artifact Registry; Looker Studio; measuring bytes scanned before and after partitioning. | P3 finish: dbt packaged in a container, run as a Cloud Run job on Cloud Scheduler with a service account and Secret Manager. Looker Studio dashboard, cost notes, README, case study. | Add P2 and P3 to the portfolio. 3 proposals. |
| Week 15 4 Jan – 10 Jan 20 h | Data quality & dbt testing | Singular and generic tests, dbt unit tests, model contracts, source freshness, intro to the dbt Semantic Layer. | Add unit tests, contracts and freshness checks to P2. | 3–5 proposals. Follow up on any viewed proposals. |
| Week 16 11 Jan – 17 Jan 15 h | Review & buffer | Catch up on anything behind. Review weak spots from the Skills sheet. | Clean GitHub, write a GitHub profile README that links all projects. Mid-phase retrospective. | Review proposal stats: views, replies, interviews. Improve the weakest template. |

Phase 3: Batch ELT deployed on AWS  (weeks 17–26)

AWS for data (IAM, S3, networking, secrets, compute) with Terraform, Airbyte and dlt ingestion, Airflow, Snowpipe. Pipelines run in the cloud, not on your laptop.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 17 18 Jan – 24 Jan 20 h | Ingestion with Airbyte | Self-hosting Airbyte on EC2 with Docker, connectors, sync modes (full refresh, incremental append, incremental dedup), CDC concepts. Fivetran concepts and pricing model. | Airbyte on an EC2 instance (Docker), syncing MySQL/Postgres into Snowflake. | 3–5 proposals. Include 'Airbyte / ELT setup' jobs where your DevOps skills help. |
| Week 18 25 Jan – 31 Jan 20 h | Custom extractors with dlt | dlt (data load tool): REST sources, pagination, rate limits, incremental cursors, schema evolution, secrets handling. | dlt pipeline from a public API into Snowflake with incremental loading. | 3–5 proposals. |
| Week 19 1 Feb – 7 Feb 20 h · P4 | Project 4: SaaS data ingestion | Stripe data model (customers, subscriptions, invoices), CRM data basics. | P4: generate Stripe test-mode data with a script, plus CRM and targets data; load all into Snowflake with dlt/Airbyte. | 3–5 proposals. |
| Week 20 8 Feb – 14 Feb 20 h · P4 | Project 4: SaaS metrics | MRR, churn, expansion, contraction, cohort retention, LTV definitions. | P4 finish: dbt metric models, dashboard, README, case study. | Add P4 to portfolio. 3–5 proposals. |
| Week 21 15 Feb – 21 Feb 20 h | Orchestration with Airflow | DAGs, operators, TaskFlow API, scheduling, retries, connections, Astronomer Cosmos for dbt. Deployment options on AWS: Airflow on EC2/ECS vs Amazon MWAA (managed, costs more). Dagster at a concept level. | Airflow running P4 end to end on a daily schedule, locally first, ready to move to AWS in week 23. | 3–5 proposals. Airflow setup jobs are a good bridge from DevOps. |
| Week 22 22 Feb – 28 Feb 20 h | AWS for data engineering + Terraform | Refresh from your Cloud Practitioner/SA study, applied to data: IAM roles and least privilege, S3 layouts and lifecycle rules, VPC and security groups, Secrets Manager, Lambda, ECS Fargate, CloudWatch logs and alarms, SNS. Terraform AWS provider, remote state. | Terraform module: S3 data buckets, IAM role for a Snowflake storage integration, SQS event notification for Snowpipe auto-ingest, Secrets Manager entries, budget alarm. | 3–5 proposals. Add AWS data skills to your profile; your Cloud Practitioner certificate supports them. |
| Week 23 1 Mar – 7 Mar 20 h · P5 | Project 5: pipeline deployed on AWS | Idempotent loads, backfills, incremental models on large tables. Running Airflow on AWS: ECS Fargate or EC2 for the portfolio, MWAA briefly for a demo then destroy it. | P5: monthly NYC TLC Parquet files → S3 → Snowpipe → Snowflake → dbt incremental models, orchestrated by Airflow running on AWS, all created with Terraform. | 3–5 proposals. |
| Week 24 8 Mar – 14 Mar 20 h · P5 | Project 5 delivery | CloudWatch alarms and SNS/Slack alerts on failure, rerun safety, cost per run, terraform destroy and recreate. | P5 finish: backfill of 12+ months, alerts, architecture diagram of the AWS setup, monthly AWS cost estimate, README, case study. | Add P5 to portfolio as "production pipeline on AWS". 3–5 proposals. |
| Week 25 15 Mar – 21 Mar 20 h · P6 | Project 6: MySQL → Snowflake migration | Schema and data type mapping, initial load strategies, incremental sync, reconciliation (row counts, checksums, aggregates). AWS DMS at a concept level. | P6: migrate a realistic MySQL database running on Amazon RDS into Snowflake (Sakila scaled up or the MySQL employees sample). | Draft a fixed-price offer: 'MySQL to Snowflake/BigQuery migration'. It uses your existing reviews. |
| Week 26 22 Mar – 28 Mar 20 h · P6 | Project 6 delivery + mid-year review | Cutover planning, runbooks, validation reports. | P6 finish: cutover runbook, validation report, cost comparison, case study. | Publish the migration offer in the Project Catalog ("MySQL / RDS to Snowflake"). Mid-year review of rate and win rate. |

Phase 4: Streaming & AWS lakehouse  (weeks 27–36)

Kafka and CDC from MySQL into Snowflake, then a serverless lakehouse on AWS with Glue (PySpark), Athena and Iceberg. Start AWS Data Engineer certification study.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 27 29 Mar – 4 Apr 20 h | Kafka fundamentals | Topics, partitions, consumer groups, offsets, delivery semantics. Run Kafka or Redpanda in Docker. Python producers and consumers. | Producer/consumer exercise with an order-event generator. | 3–5 proposals. Keep 1 active client if possible. |
| Week 28 5 Apr – 11 Apr 20 h · P7 | CDC with Debezium | MySQL binlog configuration (your strength), Kafka Connect, Debezium MySQL connector, schema registry basics. | Debezium capturing inserts, updates and deletes from MySQL into Kafka topics. | 3–5 proposals. |
| Week 29 12 Apr – 18 Apr 20 h · P7 | Streams into the warehouse | Snowflake Kafka connector and Snowpipe Streaming, Dynamic Tables, late-arriving data, deduplication. AWS options at a concept level: Amazon MSK Serverless, Kinesis Data Streams, Firehose. | Kafka topics landing in Snowflake with Dynamic Tables on top. | 3–5 proposals. |
| Week 30 19 Apr – 25 Apr 20 h · P7 | Project 7: real-time CDC build | End-to-end latency, ordering, handling deletes. | P7: order-app simulator in MySQL → Debezium → Kafka → Snowflake → Dynamic Tables/dbt. | 3–5 proposals. |
| Week 31 26 Apr – 2 May 20 h · P7 | Project 7 delivery | Measuring latency, failure and replay testing. | P7 finish: near-real-time dashboard, latency measurements, failure test notes, README, case study. | Add P7 to portfolio. Add 'real-time / CDC' to your profile. |
| Week 32 3 May – 9 May 20 h · P8 | Spark & AWS Glue fundamentals | PySpark DataFrames, partitions, shuffles, joins, caching, file formats. AWS Glue jobs and Glue Data Catalog, crawlers, Athena, EMR Serverless at a concept level. | PySpark exercises locally, then the same job as an AWS Glue job reading from S3. | 3–5 proposals. |
| Week 33 10 May – 16 May 20 h · P8 | Project 8: serverless lakehouse on AWS | Apache Iceberg tables on S3, partitioning, small-files problem, Athena query costs (bytes scanned), Lake Formation basics. | P8: Glue PySpark jobs process multiple years of NYC taxi data into Iceberg tables on S3; query with Athena; orchestrate with Step Functions or Airflow; Terraform for everything. | 3–5 proposals. |
| Week 34 17 May – 23 May 20 h · P8 | Project 8 delivery + Structured Streaming | Spark Structured Streaming basics, reading from Kafka. Comparing Athena cost vs Snowflake for the same queries. | P8 finish: Athena dashboard queries, cost comparison with Snowflake, small Structured Streaming job reading P7's topic. README, case study. | Add P8 to portfolio. Target AWS Glue / Athena jobs, which are common on Upwork. |
| Week 35 24 May – 30 May 15 h | Lakehouse & open table formats | Iceberg and Delta Lake, Iceberg tables in Snowflake and BigQuery, when a lakehouse makes sense vs a warehouse. | Write a comparison article (LinkedIn or blog) as a portfolio piece. | Share the article on LinkedIn. 3–5 proposals. |
| Week 36 31 May – 6 Jun 15 h | Review & buffer | Catch up. Start AWS Certified Data Engineer – Associate study (30 min/day from now): Kinesis, Glue, Redshift, Lake Formation, security. | Retrospective. Update the Skills sheet and GitHub profile. | Review rate: move to $30–35/hr if you have 3+ good reviews in the niche. |

Phase 5: Client-ready specialization  (weeks 37–46)

Cost optimization, observability, a productized e-commerce offer, BI and semantic layer, Redshift, secure CI/CD to AWS, consulting skills, AWS certification.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 37 7 Jun – 13 Jun 20 h · P9 | Warehouse cost & performance | Snowflake query profile, warehouse sizing, clustering keys, caching, resource monitors. BigQuery bytes-scanned optimization and slots. | Cost baseline measurements on P5. | 3–5 proposals. Target 'reduce Snowflake/BigQuery cost' jobs. |
| Week 38 14 Jun – 20 Jun 20 h · P9 | Project 9: cost audit | Writing an audit report for a non-technical client. | P9: deliberately inefficient setup → measure → optimize → before/after report with credits saved. | Turn P9 into a fixed-price 'warehouse cost audit' offer. |
| Week 39 21 Jun – 27 Jun 20 h | Data observability | Elementary (dbt package), freshness and volume anomalies, alerting. Great Expectations at a concept level. | Add Elementary monitoring to P2 and P5. | 3–5 proposals. |
| Week 40 28 Jun – 4 Jul 20 h · P10 | Project 10: e-commerce starter kit | Shopify data model (orders, line items, customers, refunds). Create a free Shopify development store for test data. | P10: reusable dbt project template for Shopify-style stores, standard marts, dashboard template. | 3–5 proposals. |
| Week 41 5 Jul – 11 Jul 20 h · P10 | Project 10: productize it | Packaging a service: scope, tiers, timelines. | P10 finish: README, setup guide, demo video. | Publish a Project Catalog offer with 3 fixed-price tiers based on P10. |
| Week 42 12 Jul – 18 Jul 20 h | BI & semantic layer | Power BI data modeling basics, Looker/LookML concepts, dbt Semantic Layer, writing a metrics definitions document with stakeholders. | Metrics definitions doc and semantic models for P2. | 3–5 proposals. |
| Week 43 19 Jul – 25 Jul 15 h · P11 | Project 11: Redshift on AWS | Redshift Serverless, distribution and sort keys, COPY from S3, Redshift Spectrum on your P8 Iceberg/S3 data, differences from Snowflake. | P11: port P2 to Redshift Serverless with Terraform (use trial credits), query P8 data through Spectrum, document the differences. | Add Redshift to profile skills with P11 as proof. |
| Week 44 26 Jul – 1 Aug 20 h | Secure CI/CD to AWS | GitHub Actions with OIDC to AWS (no stored keys), Terraform plan/apply in CI, Terraform Snowflake provider, dev/prod environments. | CI pipeline that deploys the P5 infrastructure and dbt to dev and prod, plus a Terraform module that sets up Snowflake roles and warehouses for a new client. | 3–5 proposals. |
| Week 45 2 Aug – 8 Aug 15 h | Consulting skills | Discovery calls, scoping, estimating, statements of work, handover documentation. | Discovery-call checklist, estimate template, handover template. | Refresh all proposal templates using what worked so far. |
| Week 46 9 Aug – 15 Aug 15 h | AWS certification & review | AWS Data Engineer – Associate practice exams, then take the exam. Start SnowPro Core study. | Take the AWS Certified Data Engineer – Associate exam. Retrospective. Book SnowPro and dbt exams for week 51. | Add the AWS certificate to your profile. Rate review: move to $40–45/hr if win rate holds. |

Phase 6: Capstone, certification & launch  (weeks 47–52)

One full modern data platform deployed on AWS with Terraform as your flagship project, Snowflake and dbt exams, portfolio polish and a rate increase.

| Week | Focus | Learn | Build | Upwork |
| --- | --- | --- | --- | --- |
| Week 47 16 Aug – 22 Aug 20 h · P12 | Capstone design | Architecture decision records, requirements writing. | P12: requirements, architecture diagram, Terraform for all AWS and Snowflake environments. | 3–5 proposals. Keep active clients happy first. |
| Week 48 23 Aug – 29 Aug 20 h · P12 | Capstone build I | — | P12: batch ingestion (dlt/Airbyte) plus CDC stream; dbt staging and marts. | 3–5 proposals. |
| Week 49 30 Aug – 5 Sep 20 h · P12 | Capstone build II | — | P12: Airflow on AWS, GitHub Actions with OIDC deploys, Elementary monitoring, CloudWatch alerts, dashboard. | 3–5 proposals. |
| Week 50 6 Sep – 12 Sep 20 h · P12 | Capstone delivery | Recording a clear walkthrough video. | P12 finish: runbook, docs, 5-minute walkthrough video, case study. | Make P12 the first item in your portfolio. |
| Week 51 13 Sep – 19 Sep 15 h | Certification week | Final review. | Take SnowPro Core and the dbt Analytics Engineering exam. | Add certifications to your profile. |
| Week 52 20 Sep – 26 Sep 15 h | Launch & year-2 plan | — | Portfolio polish, update every case study with results. Year retrospective. Write the year-2 plan. | Raise your rate to $45–50/hr for new clients. Set year-2 targets. |

# 5. Project briefs

Twelve projects, each built around a business story. Clients hire for outcomes, so every README and case study should open with the problem, not the tools.

## P1. Sakila: from MySQL to a star schema

| Weeks | 3–6 |
| --- | --- |
| Business story | A DVD rental chain runs everything on MySQL and can't answer basic questions: which films earn most, which stores perform best, which customers churn. |
| Data | MySQL Sakila sample database |
| Stack | MySQL, DuckDB, dbt-duckdb, Metabase (Docker) |
| Deliverables | Bus matrix, star schema (fct_rentals, fct_payments, dims), dbt tests and docs, Metabase dashboard, README |
| Done when | dbt build passes with tests on every primary key; dashboard answers 5 business questions |
| Upwork jobs it proves | Data modeling, reporting on top of MySQL, 'turn my database into dashboards' jobs |

## P2. Olist marketplace analytics on Snowflake

| Weeks | 7–11, 15 |
| --- | --- |
| Business story | A marketplace wants one trusted source for revenue, delivery performance and seller quality. |
| Data | Brazilian E-Commerce Public Dataset by Olist (Kaggle) |
| Stack | Snowflake, dbt Core, GitHub Actions, SQLFluff, Metabase/Power BI |
| Deliverables | Staged, intermediate and mart models; snapshots; unit tests and contracts; CI; dashboard; case study |
| Done when | CI runs on every pull request; dashboard shows revenue, AOV, delivery SLA, seller scores |
| Upwork jobs it proves | Core Snowflake + dbt jobs, the most common analytics engineer post |

## P3. GA4 marketing analytics on BigQuery (Google Cloud)

| Weeks | 12–14 |
| --- | --- |
| Business story | An online store wants to understand sessions, funnels and which channels bring buyers. |
| Data | bigquery-public-data.ga4_obfuscated_sample_ecommerce |
| Stack | BigQuery, dbt-bigquery, Docker, Cloud Run jobs, Cloud Scheduler, Secret Manager, Looker Studio |
| Deliverables | Session and funnel models, channel grouping, dbt running on a schedule in Google Cloud, dashboard, cost notes on partitioning |
| Done when | Funnel from session to purchase by channel; dbt runs daily in Cloud Run without your laptop; documented bytes-scanned savings |
| Upwork jobs it proves | GA4/BigQuery jobs and Google Cloud deployment, common with marketing agencies and small stores |

## P4. SaaS revenue metrics (MRR, churn, LTV)

| Weeks | 19–20 |
| --- | --- |
| Business story | A SaaS founder needs MRR, churn and cohort retention without paying for an expensive tool. |
| Data | Stripe test-mode data generated by script, CRM data, targets sheet |
| Stack | Python, dlt, Airbyte, Snowflake, dbt, Airflow (added week 21) |
| Deliverables | Ingestion pipelines, MRR movement and cohort models, dashboard, case study |
| Done when | MRR bridge (new, expansion, contraction, churn) reconciles to raw invoices |
| Upwork jobs it proves | Stripe/SaaS metrics jobs, multi-source ELT |

## P5. NYC Taxi pipeline deployed on AWS

| Weeks | 23–24 |
| --- | --- |
| Business story | A city operations team needs monthly trip, revenue and zone metrics that refresh automatically. |
| Data | NYC TLC Trip Record Data (monthly Parquet files) |
| Stack | Terraform, S3, SQS + Snowpipe, Snowflake, dbt incremental, Airflow on ECS Fargate/EC2 (MWAA demo), CloudWatch, SNS alerts |
| Deliverables | Pipeline running on AWS built with Terraform, 12+ months backfill, alerts, AWS architecture diagram, monthly cost estimate, case study |
| Done when | terraform apply creates everything from scratch; reruns are idempotent; a failed run sends an alert |
| Upwork jobs it proves | Production batch ELT on AWS, the most requested cloud for data jobs |

## P6. MySQL to Snowflake migration

| Weeks | 25–26 |
| --- | --- |
| Business story | A company outgrew MySQL reporting and wants to move analytics to Snowflake without losing data. |
| Data | MySQL employees sample database or a scaled-up Sakila, hosted on Amazon RDS |
| Stack | Amazon RDS for MySQL, Airbyte or dlt, Snowflake, Python reconciliation scripts |
| Deliverables | Type mapping, initial and incremental loads, reconciliation report, cutover runbook, cost comparison |
| Done when | Row counts and checksums match for every table; runbook tested once end to end |
| Upwork jobs it proves | Migration jobs that combine your DBA reviews with the new niche |

## P7. Real-time orders with CDC

| Weeks | 28–31 |
| --- | --- |
| Business story | An operations team wants order status on a dashboard within a minute, not the next morning. |
| Data | Order-app simulator writing to MySQL |
| Stack | MySQL binlog, Debezium, Kafka/Redpanda, Snowflake Kafka connector, Dynamic Tables, dbt |
| Deliverables | CDC pipeline, near-real-time dashboard, latency measurements, failure/replay notes |
| Done when | Inserts, updates and deletes appear in Snowflake within target latency; replay after failure works |
| Upwork jobs it proves | Streaming and CDC jobs, higher-rate work |

## P8. Serverless lakehouse on AWS (Glue, Athena, Iceberg)

| Weeks | 32–34 |
| --- | --- |
| Business story | An analyst team needs multi-year trends from data too large for pandas, without running servers. |
| Data | Several years of NYC TLC data (or GitHub Archive) |
| Stack | PySpark, AWS Glue jobs and Data Catalog, S3, Apache Iceberg, Athena, Step Functions or Airflow, Terraform |
| Deliverables | Iceberg tables on S3, Athena queries and dashboard, Athena vs Snowflake cost comparison, small streaming job, case study |
| Done when | Glue jobs run on the full dataset; Athena queries use partition pruning; costs documented |
| Upwork jobs it proves | AWS Glue / Athena / Spark jobs, very common on Upwork |

## P9. Warehouse cost audit

| Weeks | 37–38 |
| --- | --- |
| Business story | A client's Snowflake bill doubled and nobody knows why. |
| Data | Your P5 environment, deliberately misconfigured |
| Stack | Snowflake query history, query profile, resource monitors, dbt |
| Deliverables | Audit report with before/after credits, list of fixes, monitoring setup |
| Done when | Measured cost reduction with evidence for each change |
| Upwork jobs it proves | Cost optimization jobs, a strong fixed-price offer |

## P10. E-commerce analytics starter kit

| Weeks | 40–41 |
| --- | --- |
| Business story | Small online stores need standard reporting fast, without a custom project each time. |
| Data | Shopify development store (free) with test orders |
| Stack | Shopify API, dlt, Snowflake or BigQuery, dbt template, dashboard template |
| Deliverables | Reusable dbt project, setup guide, demo video, Project Catalog offer |
| Done when | A new store can be set up from the template in one day |
| Upwork jobs it proves | Productized service you can sell repeatedly |

## P11. Redshift on AWS

| Weeks | 43 |
| --- | --- |
| Business story | Show you can deliver on AWS-native warehouses when a client already uses Redshift. |
| Data | P2 Olist models |
| Stack | Redshift Serverless, Redshift Spectrum, S3, dbt-redshift, Terraform |
| Deliverables | Working port of P2, Spectrum queries on P8 data, notes on differences (dist/sort keys, COPY, SQL dialect) |
| Done when | dbt build passes on Redshift with the same tests as P2 |
| Upwork jobs it proves | Redshift and AWS-native warehouse jobs |

## P12. Capstone: modern data platform on AWS

| Weeks | 47–50 |
| --- | --- |
| Business story | A growing company needs a complete, maintainable data platform built from scratch. |
| Data | Combine sources from P4, P7 and P10 |
| Stack | Terraform, AWS (S3, ECS/MWAA, Secrets Manager, CloudWatch), Snowflake, dlt/Airbyte, Debezium/Kafka, dbt, Airflow, GitHub Actions with OIDC, Elementary, BI tool |
| Deliverables | Architecture diagram, Terraform for AWS and Snowflake, batch + streaming ingestion, dbt layers, CI/CD, monitoring, dashboard, runbook, 5-min video |
| Done when | Someone else could run it from your README; video explains business value in plain words |
| Upwork jobs it proves | Senior, end-to-end work that justifies $45–60/hr |

# 6. Upwork transition plan

## Keep your current income

Do not remove your DBA and DevOps work from Upwork. Those reviews are proof that you deliver. Keep taking those jobs for income until analytics work replaces them.

## Use a specialized profile

Upwork lets you add specialized profiles next to your general one. In week 11 create one titled along the lines of "Analytics Engineer | Snowflake, dbt, BigQuery" and attach only analytics projects to it. Your general profile keeps the DBA/DevOps story.

## Bridge offers first

Your fastest analytics wins will come from jobs that mix your old and new skills. Look for:

- MySQL or Postgres (including Amazon RDS) to Snowflake/BigQuery migrations (P6)

- Data pipelines on AWS: S3, Glue, Athena, Lambda, Terraform (P5, P8)

- Setting up Airflow, Airbyte or dbt on Docker or a cloud VM (DevOps + data)

- Slow SQL or slow dashboards that need query tuning

- CDC from MySQL into a warehouse (P7)

- Warehouse cost reduction (P9)

## Proposal routine

- Send 2–3 proposals per week from week 11, rising to 3–5 from week 15.

- Prefer small fixed-price jobs early. Five good reviews matter more than one big contract at this stage.

- Open with the client's problem and a short plan. Link the one project that matches their job, not all twelve.

- Log every proposal in the tracker's Upwork Pipeline sheet. Every four weeks, check which templates get replies.

## Rate ladder

Raise your rate for new clients every 2–3 successful contracts. Keep existing clients at their rate, or raise it with notice. Suggested steps: $25 → $30 → $35 → $40–45 → $45–50 by week 52, then $50–65 in year 2.

# 7. Portfolio standard

## Every project README includes

- The business problem in two or three plain sentences

- An architecture diagram (draw.io or Excalidraw is fine)

- The stack and why each tool was chosen

- The data model: a lineage graph screenshot from dbt docs

- Screenshots of the dashboard

- How to run it: setup steps someone else can follow

- What you would do next with more time

## Case study (for your Upwork portfolio)

Keep it to one page: Problem → Approach → Result → Tools. Use numbers wherever possible, such as "cut query time from 40 s to 3 s" or "reduced monthly credits by 35%". Measure these during the project so you have them later.

# 8. Learning resources

Prefer official docs and hands-on courses. Check that course and exam details are current before you start them.

| Topic | Resource |
| --- | --- |
| dbt | dbt Learn free courses (Fundamentals, Jinja & macros, advanced materializations); dbt Developer docs |
| Snowflake | Snowflake documentation and Snowflake Quickstarts; SnowPro Core study guide |
| BigQuery | Google Cloud BigQuery documentation; BigQuery sandbox; GA4 BigQuery export schema docs |
| AWS | AWS Skill Builder (free Data Engineer – Associate exam prep); AWS Well-Architected Data Analytics Lens; AWS Glue, Athena and Redshift docs; Terraform AWS provider docs |
| Google Cloud | Google Cloud Skills Boost; Cloud Run jobs and Cloud Scheduler docs |
| Modeling | The Data Warehouse Toolkit (Kimball & Ross, 3rd edition) |
| Data engineering overall | Fundamentals of Data Engineering (Reis & Housley); DataTalksClub Data Engineering Zoomcamp (free, on GitHub) |
| Ingestion | dlt (dlthub) docs; Airbyte docs |
| Orchestration | Apache Airflow docs; Astronomer Cosmos docs for dbt in Airflow |
| Streaming & CDC | Kafka documentation; Debezium MySQL connector docs; Snowflake Kafka connector docs |
| Spark | Apache Spark PySpark docs; Databricks Free Edition |
| Observability | Elementary (dbt package) docs |
| Datasets | MySQL Sakila and employees samples; Olist Brazilian E-Commerce (Kaggle); BigQuery GA4 public sample; NYC TLC Trip Record Data; Stripe test mode; Shopify development stores |

# 9. Using the tracker

The Excel tracker follows this document week by week. Its sheets:

- Dashboard: overall progress, hours, projects finished and Upwork numbers, all calculated automatically. Change the start date here and every week's dates update.

- Weekly Plan: all 52 weeks. Fill in actual hours, status, a confidence score (1–5) and notes each Sunday.

- Projects: the 12 projects with status, GitHub link, and whether the case study and Upwork portfolio item are done.

- Skills: rate yourself 1–5 each month and compare against the target level.

- Upwork Pipeline: one row per proposal: Connects, rate, whether it was viewed, interviewed and hired, and contract value.

- Monthly Review: monthly totals pulled from the other sheets plus space for what worked and what to change.

The one rule: finish projects, even imperfectly. Twelve finished, documented projects will win more work than twenty half-built ones.