## Dashboard
Analytics Engineer Roadmap — Dashboard
Everything here is calculated from the other sheets. Only the yellow cells are inputs.
Settings
Start date (Monday of week 1) | 2026-09-28
Weekly hours target (reference) | 20
Monthly income goal ($) | 5000
Today | 2026-09-23
Learning progress |  | Upwork (analytics niche)
Current week (by date) | 1 | Proposals sent | 0
Weeks marked Done | 1 | Connects spent | 0
Weeks completed % | 1.562% | Viewed | 0
Weeks behind schedule | 0 | Interviews | 0
Planned hours to date | 20 | Hired | 0
Actual hours logged | 20 | Win rate (hired / sent) | 0%
Hours vs plan | 100% | Total contract value ($) | 0
Projects done (of 14) | 0 | Average hourly rate on hires ($) | 0
Case studies written | 0 | Last logged month income ($) | 900
Average confidence (1–5) | 4 | Progress to income goal | 18%
Skills at target | 0
Phases
Phase | % done | Weeks done | Weeks in phase
1. Foundations & bridge from DBA | 16.67% | 1 | 6
2. Warehouses + dbt in depth | 0% | 0 | 11
3. BI & business analytics | 0% | 0 | 7
4. Batch ELT deployed on AWS | 0% | 0 | 11
5. Streaming & AWS lakehouse | 0% | 0 | 11
6. Client-ready specialization | 0% | 0 | 11
7. Capstone, certification & launch | 0% | 0 | 7
How to use
• Yellow cells are inputs. White cells are formulas: leave them alone.
• Every Sunday: in Weekly Plan, enter actual hours, set Status, rate confidence 1–5, add notes.
• Every proposal: add one row in Upwork Pipeline.
• End of each month: fill income and reflections in Monthly Review, and re-rate yourself in Skills.
• Row 5 of Upwork Pipeline and Projects is an example of the expected format; overwrite or delete it.
Note on B5: Change this and every week date in Weekly Plan updates.

## Weekly Plan
Weekly Plan — 64 weeks
Dates follow the start date on the Dashboard. Fill the yellow columns each Sunday.
Week | Start | Phase | Focus | Planned h | Actual h | Status | Confidence (1–5) | Project | Learn | Build | Upwork action | Notes / blockers
1 | 2026-09-28 | 1 | Advanced analytical SQL I | 20 | 20 | Done | 4 |  | Window functions (ROW_NUMBER, RANK, LAG/LEAD, running totals), CTEs, QUALIFY, GROUPING SETS/ROLLUP, CASE-based pivots. Install DuckDB and practice locally for free. | Solve 30 analytical SQL exercises on a sample dataset; push to a GitHub repo 'sql-analytics-practice'. | Audit your current profile. List the past DBA/DevOps jobs that support an analytics story (SQL tuning, MySQL, Docker, Linux). | Example row: replace with your own. Window functions solid; GROUPING SETS needs review.
2 | 2026-10-05 | 1 | Advanced analytical SQL II | 20 |  | Not started |  |  | Analytics patterns: cohorts, retention, funnels, sessionization, gaps-and-islands, date spines, deduplication, percentiles. Reading query plans in a columnar engine vs MySQL. | Add 20 pattern exercises with written explanations to the practice repo. | Save 20 real analytics engineer / dbt / Snowflake job posts to a research list. Note tools, budgets and wording.
3 | 2026-10-12 | 1 | Dimensional modeling (Kimball) | 20 |  | Not started |  | P1 | Grain, fact types (transaction, periodic snapshot, accumulating), conformed dimensions, surrogate keys, SCD types 1/2, bus matrix, one-big-table vs star schema. | P1 starts: design a bus matrix and star schema for the MySQL Sakila sample database. | Summarize the 20 saved posts: top 10 recurring requirements. Adjust the plan if something big is missing.
4 | 2026-10-19 | 1 | Python for data work | 20 |  | Not started |  |  | pandas or polars basics, requests, API pagination and retries, environment variables and secrets, logging, pytest, project structure with virtual environments. | Python extractor exercise: a public REST API to Parquet files, with tests and logging. | Keep taking DBA/DevOps work for income. No new-niche bids yet.
5 | 2026-10-26 | 1 | dbt fundamentals | 20 |  | Not started |  | P1 | dbt-duckdb setup, project structure (staging / intermediate / marts), sources, ref, materializations, generic tests, docs, seeds. Complete the free dbt Fundamentals course. | P1: staging and intermediate models for Sakila in dbt on DuckDB. | Draft a new headline and overview that bridge 'MySQL DBA' to 'data warehouse / analytics'.
6 | 2026-11-02 | 1 | Project 1 delivery | 20 |  | Not started |  | P1 | Metabase basics (run in Docker), writing a project README, drawing a simple architecture diagram. | P1 finish: fact and dimension marts, tests, dbt docs, Metabase dashboard, README with business story. | Add P1 to your portfolio. Update your profile with the bridge headline.
7 | 2026-11-09 | 2 | Snowflake architecture | 20 |  | Not started |  | P2 | Virtual warehouses, micro-partitions, RBAC and roles, stages, file formats, COPY INTO, time travel, zero-copy cloning, credit usage, resource monitors, auto-suspend. | Start the Snowflake free trial. On day one set Snowflake resource monitors and an AWS Budgets alarm on your AWS account. Load the Olist CSVs through a stage with COPY INTO. Script your roles and warehouses. | Take the Snowflake-related Upwork skill tags into your profile once you have used them.
8 | 2026-11-16 | 2 | dbt intermediate | 20 |  | Not started |  | P2 | Incremental models (merge strategy, is_incremental), snapshots for SCD2, Jinja and macros, packages (dbt_utils, dbt_expectations), exposures. | P2: staging and intermediate models for Olist on Snowflake. | Read 10 winning-style proposals in the analytics category (profiles of top freelancers) and note their structure.
9 | 2026-11-23 | 2 | Project 2: marts & tests | 20 |  | Not started |  | P2 | Designing marts for business questions, naming conventions, test coverage strategy. | P2: fct_orders, fct_order_items, dim_customers, dim_sellers, dim_products, dim_date with tests. | Write 3 proposal templates: dbt fix, SQL optimization, dashboard + model.
10 | 2026-11-30 | 2 | Project 2: metrics & dashboard | 20 |  | Not started |  | P2 | Metric definitions (revenue, AOV, delivery SLA, repeat rate), Metabase questions and dashboards. | P2: first dashboard in Metabase for revenue, delivery performance, seller performance and review score vs delay (rebuilt properly in Power BI in P4). Publish dbt docs. | Prepare the specialized profile text: 'Analytics Engineer ¦ Snowflake + dbt'.
11 | 2026-12-07 | 2 | CI/CD for dbt | 20 |  | Not started |  | P2 | GitHub Actions for dbt build on pull requests, slim CI with state:modified, separate dev and prod targets, pre-commit and SQLFluff linting. | P2 finish: CI pipeline, README, one-page case study. | Publish the specialized profile. Start 2–3 proposals per week on small dbt/SQL/dashboard jobs.
12 | 2026-12-14 | 2 | BigQuery fundamentals | 20 |  | Not started |  | P3 | Storage vs compute, partitioning and clustering, on-demand pricing (bytes scanned), nested fields (STRUCT, ARRAY, UNNEST), the free sandbox. GCP basics: projects, IAM, service accounts, Cloud Storage, billing budgets. | Explore the public GA4 sample dataset (bigquery-public-data.ga4_obfuscated_sample_ecommerce). | 3 proposals. Track every one in the Upwork Pipeline sheet.
13 | 2026-12-21 | 2 | Project 3: GA4 modeling | 20 |  | Not started |  | P3 | GA4 event schema, flattening event_params, sessionization, channel grouping, funnels. | P3: dbt-bigquery project with sessions, events and funnel models. | 3 proposals. Prefer fixed-price jobs under $300 for fast reviews.
14 | 2026-12-28 | 2 | Project 3: Looker Studio dashboard | 20 |  | Not started |  | P3 | Looker Studio: data sources on BigQuery, calculated fields, filters and controls, blending, sharing. Measuring bytes scanned before and after partitioning. | P3: marketing funnel dashboard in Looker Studio, cost notes on partitioning. | Add P2 to the portfolio. 3 proposals.
15 | 2027-01-04 | 2 | Project 3: deploy on Google Cloud | 20 |  | Not started |  | P3 | Cloud Run jobs, Cloud Scheduler, Secret Manager, Artifact Registry, service accounts with least privilege. | P3 finish: dbt packaged in a container, run daily as a Cloud Run job on Cloud Scheduler with Secret Manager. README, case study. | Add P3 to the portfolio. 3 proposals.
16 | 2027-01-11 | 2 | Data quality & dbt testing | 20 |  | Not started |  |  | Singular and generic tests, dbt unit tests, model contracts, source freshness, intro to the dbt Semantic Layer. | Add unit tests, contracts and freshness checks to P2. | 3–5 proposals. Follow up on any viewed proposals.
17 | 2027-01-18 | 2 | Review & buffer | 15 |  | Not started |  |  | Catch up on anything behind. Review weak spots from the Skills sheet. | Clean GitHub, write a GitHub profile README that links all projects. Mid-phase retrospective. | Review proposal stats: views, replies, interviews. Improve the weakest template.
18 | 2027-01-25 | 3 | Power BI fundamentals | 20 |  | Not started |  | P4 | Power BI Desktop, Power Query, star-schema data model, relationships, Import vs DirectQuery, connecting to Snowflake and BigQuery, publishing to the Power BI Service (use the free trial). | Connect Power BI to your P2 Snowflake marts; build the model on top of dbt facts and dimensions (no transformations in Power BI). | 3–5 proposals. Start including small "Power BI dashboard" jobs.
19 | 2027-02-01 | 3 | DAX essentials | 20 |  | Not started |  | P4 | Measures vs calculated columns, CALCULATE and filter context, a proper date table, time intelligence (YTD, MoM, YoY), ranking, basic performance rules. | Write the measures for P4: revenue, orders, AOV, growth %, repeat-customer rate, delivery SLA. | 3–5 proposals.
20 | 2027-02-08 | 3 | Dashboard design & storytelling | 20 |  | Not started |  | P4 | Chart choice, KPI cards, layout for executives vs analysts, color and accessibility, drill-through, tooltips, mobile layout. Read "Storytelling with Data" (Knaflic). | Sketch the P4 pages on paper first: executive overview, products, customers, delivery. | 3–5 proposals. Save 10 good dashboard examples from Upwork portfolios.
21 | 2027-02-15 | 3 | Project 4: sales analytics in Power BI | 20 |  | Not started |  | P4 | Sales KPIs: revenue, AOV, product and category mix, RFM customer segments, cohorts, geography. Row-level security, scheduled refresh. | P4 finish: multi-page Power BI sales dashboard on Snowflake with row-level security per seller, scheduled refresh, 3-minute demo video, case study. | Add P4 to portfolio. Create a "Power BI on Snowflake/BigQuery" specialized profile section.
22 | 2027-02-22 | 3 | Marketing analytics domain | 20 |  | Not started |  | P5 | Ad platform data (Google Ads, Meta Ads), UTM parameters, CAC, ROAS, CPA, attribution models (last-click, first-click, linear), blended vs platform-reported numbers. | P5 starts: generate realistic Google/Meta ad-spend data by campaign and day matching the GA4 sample dates; load to BigQuery; dbt staging. | 3–5 proposals. Look at marketing-agency job posts and note what they measure.
23 | 2027-03-01 | 3 | Project 5: marketing performance | 20 |  | Not started |  | P5 | Joining sessions, orders and ad spend by channel and campaign; handling attribution windows; one source of truth vs ad platform numbers. | P5 finish: dbt marts for campaign performance, Looker Studio dashboard (ROAS, CAC, spend vs revenue by channel), plus a Power BI version of the executive page. Case study. | Add P5 to portfolio. Draft a fixed-price "marketing dashboard" offer.
24 | 2027-03-08 | 3 | BI review & offers | 15 |  | Not started |  |  | Review weak DAX topics. Power BI performance basics (aggregations, reducing model size). | Polish P4 and P5 screenshots and videos. Retrospective. | Publish two Project Catalog offers: "Power BI sales dashboard" and "Marketing performance dashboard". Review proposal stats.
25 | 2027-03-15 | 4 | Ingestion with Airbyte | 20 |  | Not started |  |  | Self-hosting Airbyte on EC2 with Docker, connectors, sync modes (full refresh, incremental append, incremental dedup), CDC concepts. Fivetran concepts and pricing model. | Airbyte on an EC2 instance (Docker), syncing MySQL/Postgres into Snowflake. | 3–5 proposals. Include 'Airbyte / ELT setup' jobs where your DevOps skills help.
26 | 2027-03-22 | 4 | Custom extractors with dlt | 20 |  | Not started |  |  | dlt (data load tool): REST sources, pagination, rate limits, incremental cursors, schema evolution, secrets handling. | dlt pipeline from a public API into Snowflake with incremental loading. | 3–5 proposals.
27 | 2027-03-29 | 4 | Project 4: SaaS data ingestion | 20 |  | Not started |  | P6 | Stripe data model (customers, subscriptions, invoices), CRM data basics. | P6: generate Stripe test-mode data with a script, plus CRM and targets data; load all into Snowflake with dlt/Airbyte. | 3–5 proposals.
28 | 2027-04-05 | 4 | Project 4: SaaS metrics | 20 |  | Not started |  | P6 | MRR, churn, expansion, contraction, cohort retention, LTV definitions. | P6 finish: dbt metric models, Power BI SaaS dashboard (MRR bridge, churn, cohort retention heatmap), README, case study. | Add P6 to portfolio. 3–5 proposals.
29 | 2027-04-12 | 4 | Orchestration with Airflow | 20 |  | Not started |  |  | DAGs, operators, TaskFlow API, scheduling, retries, connections, Astronomer Cosmos for dbt. Deployment options on AWS: Airflow on EC2/ECS vs Amazon MWAA (managed, costs more). Dagster at a concept level. | Airflow running P6 end to end on a daily schedule, locally first, ready to move to AWS in week 32. | 3–5 proposals. Airflow setup jobs are a good bridge from DevOps.
30 | 2027-04-19 | 4 | AWS for data engineering | 20 |  | Not started |  |  | Refresh from your Cloud Practitioner/SA study, applied to data: IAM roles and least privilege, S3 layouts and lifecycle rules, VPC and security groups, Secrets Manager, Lambda, ECS Fargate, CloudWatch logs and alarms, SNS. | Hands-on: S3 buckets, IAM roles, a Lambda that lands API data in S3, CloudWatch alarm to SNS email. Budget alarm checked. | 3–5 proposals. Add AWS data skills to your profile; your Cloud Practitioner certificate supports them.
31 | 2027-04-26 | 4 | Terraform for AWS data infrastructure | 20 |  | Not started |  |  | Terraform AWS provider, modules, remote state in S3, variables per environment, terraform destroy discipline. | Terraform module: S3 data buckets, IAM role for a Snowflake storage integration, SQS event notification for Snowpipe auto-ingest, Secrets Manager entries, budget alarm. | 3–5 proposals.
32 | 2027-05-03 | 4 | Project 7: pipeline deployed on AWS | 20 |  | Not started |  | P7 | Idempotent loads, backfills, incremental models on large tables. Running Airflow on AWS: ECS Fargate or EC2 for the portfolio, MWAA briefly for a demo then destroy it. | P7: monthly NYC TLC Parquet files → S3 → Snowpipe → Snowflake → dbt incremental models, orchestrated by Airflow running on AWS, all created with Terraform. | 3–5 proposals.
33 | 2027-05-10 | 4 | Project 5 delivery | 20 |  | Not started |  | P7 | CloudWatch alarms and SNS/Slack alerts on failure, rerun safety, cost per run, terraform destroy and recreate. | P7 finish: backfill of 12+ months, alerts, Power BI operations dashboard (trips, revenue, zones), AWS architecture diagram, monthly cost estimate, README, case study. | Add P7 to portfolio as "production pipeline on AWS". 3–5 proposals.
34 | 2027-05-17 | 4 | Project 6: MySQL → Snowflake migration | 20 |  | Not started |  | P8 | Schema and data type mapping, initial load strategies, incremental sync, reconciliation (row counts, checksums, aggregates). AWS DMS at a concept level. | P8: migrate a realistic MySQL database running on Amazon RDS into Snowflake (Sakila scaled up or the MySQL employees sample). | Draft a fixed-price offer: 'MySQL to Snowflake/BigQuery migration'. It uses your existing reviews.
35 | 2027-05-24 | 4 | Project 6 delivery + mid-year review | 20 |  | Not started |  | P8 | Cutover planning, runbooks, validation reports. | P8 finish: cutover runbook, validation report, cost comparison, case study. | Publish the migration offer in the Project Catalog ("MySQL / RDS to Snowflake"). Mid-year review of rate and win rate.
36 | 2027-05-31 | 5 | Kafka fundamentals | 20 |  | Not started |  |  | Topics, partitions, consumer groups, offsets, delivery semantics. Run Kafka or Redpanda in Docker. Python producers and consumers. | Producer/consumer exercise with an order-event generator. | 3–5 proposals. Keep 1 active client if possible.
37 | 2027-06-07 | 5 | CDC with Debezium | 20 |  | Not started |  | P9 | MySQL binlog configuration (your strength), Kafka Connect, Debezium MySQL connector, schema registry basics. | Debezium capturing inserts, updates and deletes from MySQL into Kafka topics. | 3–5 proposals.
38 | 2027-06-14 | 5 | Streams into the warehouse | 20 |  | Not started |  | P9 | Snowflake Kafka connector and Snowpipe Streaming, Dynamic Tables, late-arriving data, deduplication. AWS options at a concept level: Amazon MSK Serverless, Kinesis Data Streams, Firehose. | Kafka topics landing in Snowflake with Dynamic Tables on top. | 3–5 proposals.
39 | 2027-06-21 | 5 | Project 7: real-time CDC build | 20 |  | Not started |  | P9 | End-to-end latency, ordering, handling deletes. | P9: order-app simulator in MySQL → Debezium → Kafka → Snowflake → Dynamic Tables/dbt. | 3–5 proposals.
40 | 2027-06-28 | 5 | Project 7 delivery | 20 |  | Not started |  | P9 | Measuring latency, failure and replay testing. | P9 finish: near-real-time dashboard, latency measurements, failure test notes, README, case study. | Add P9 to portfolio. Add 'real-time / CDC' to your profile.
41 | 2027-07-05 | 5 | Buffer & catch-up | 15 |  | Not started |  |  | Catch up on anything behind from Kafka, CDC and Snowflake streaming. | Fix loose ends in P9. Add a near-real-time ops page in Power BI (DirectQuery) on top of it. | 3–5 proposals.
42 | 2027-07-12 | 5 | Spark & AWS Glue fundamentals | 20 |  | Not started |  | P10 | PySpark DataFrames, partitions, shuffles, joins, caching, file formats. AWS Glue jobs and Glue Data Catalog, crawlers, Athena, EMR Serverless at a concept level. | PySpark exercises locally, then the same job as an AWS Glue job reading from S3. | 3–5 proposals.
43 | 2027-07-19 | 5 | Project 8: serverless lakehouse on AWS | 20 |  | Not started |  | P10 | Apache Iceberg tables on S3, partitioning, small-files problem, Athena query costs (bytes scanned), Lake Formation basics. | P10: Glue PySpark jobs process multiple years of NYC taxi data into Iceberg tables on S3; query with Athena; orchestrate with Step Functions or Airflow; Terraform for everything. | 3–5 proposals.
44 | 2027-07-26 | 5 | Project 8 delivery + Structured Streaming | 20 |  | Not started |  | P10 | Spark Structured Streaming basics, reading from Kafka. Comparing Athena cost vs Snowflake for the same queries. | P10 finish: Athena dashboard queries, cost comparison with Snowflake, small Structured Streaming job reading P9's topic. README, case study. | Add P10 to portfolio. Target AWS Glue / Athena jobs, which are common on Upwork.
45 | 2027-08-02 | 5 | Lakehouse & open table formats | 15 |  | Not started |  |  | Iceberg and Delta Lake, Iceberg tables in Snowflake and BigQuery, when a lakehouse makes sense vs a warehouse. | Write a comparison article (LinkedIn or blog) as a portfolio piece. | Share the article on LinkedIn. 3–5 proposals.
46 | 2027-08-09 | 5 | Review & buffer | 15 |  | Not started |  |  | Catch up. Start AWS Certified Data Engineer – Associate study (30 min/day from now): Kinesis, Glue, Redshift, Lake Formation, security. | Retrospective. Update the Skills sheet and GitHub profile. | Review rate: move to $30–35/hr if you have 3+ good reviews in the niche.
47 | 2027-08-16 | 6 | Warehouse cost & performance | 20 |  | Not started |  | P11 | Snowflake query profile, warehouse sizing, clustering keys, caching, resource monitors. BigQuery bytes-scanned optimization and slots. | Cost baseline measurements on P7. | 3–5 proposals. Target 'reduce Snowflake/BigQuery cost' jobs.
48 | 2027-08-23 | 6 | Project 9: cost audit | 20 |  | Not started |  | P11 | Writing an audit report for a non-technical client. | P11: deliberately inefficient setup → measure → optimize → before/after report with credits saved. | Turn P11 into a fixed-price 'warehouse cost audit' offer.
49 | 2027-08-30 | 6 | Data observability | 20 |  | Not started |  |  | Elementary (dbt package), freshness and volume anomalies, alerting. Great Expectations at a concept level. | Add Elementary monitoring to P2 and P7. | 3–5 proposals.
50 | 2027-09-06 | 6 | Project 10: e-commerce starter kit | 20 |  | Not started |  | P12 | Shopify data model (orders, line items, customers, refunds). Create a free Shopify development store for test data. | P12: reusable dbt project template for Shopify-style stores, standard marts, plus a Power BI template (.pbit) and a Looker Studio template. | 3–5 proposals.
51 | 2027-09-13 | 6 | Project 10: productize it | 20 |  | Not started |  | P12 | Packaging a service: scope, tiers, timelines. | P12 finish: README, setup guide, demo video showing data flowing from Shopify to the dashboards. | Publish a Project Catalog offer with 3 fixed-price tiers based on P12.
52 | 2027-09-20 | 6 | Semantic layer & BI at scale | 20 |  | Not started |  |  | dbt Semantic Layer, one metric definition used by several tools, Power BI incremental refresh and aggregations, Looker/LookML concepts, writing a metrics definitions document with stakeholders. | Metrics definitions doc and semantic models for P2; connect P4 to shared metric definitions where possible. | 3–5 proposals.
53 | 2027-09-27 | 6 | Project 11: Redshift on AWS | 15 |  | Not started |  | P13 | Redshift Serverless, distribution and sort keys, COPY from S3, Redshift Spectrum on your P10 Iceberg/S3 data, differences from Snowflake. | P13: port P2 to Redshift Serverless with Terraform (use trial credits), query P10 data through Spectrum, document the differences. | Add Redshift to profile skills with P13 as proof.
54 | 2027-10-04 | 6 | Secure CI/CD to AWS | 20 |  | Not started |  |  | GitHub Actions with OIDC to AWS (no stored keys), Terraform plan/apply in CI, Terraform Snowflake provider, dev/prod environments. | CI pipeline that deploys the P7 infrastructure and dbt to dev and prod, plus a Terraform module that sets up Snowflake roles and warehouses for a new client. | 3–5 proposals.
55 | 2027-10-11 | 6 | Consulting skills | 15 |  | Not started |  |  | Discovery calls, scoping, estimating, statements of work, handover documentation. | Discovery-call checklist, estimate template, handover template. | Refresh all proposal templates using what worked so far.
56 | 2027-10-18 | 6 | AWS exam preparation | 15 |  | Not started |  |  | AWS Data Engineer – Associate practice exams and weak-area review (Kinesis, Glue, Redshift, Lake Formation, security). | Two full practice exams; review every wrong answer. | Keep active clients happy first. 3 proposals.
57 | 2027-10-25 | 6 | AWS certification & review | 15 |  | Not started |  |  | Final review, then take the exam. Start SnowPro Core study. | Take the AWS Certified Data Engineer – Associate exam. Retrospective. Book SnowPro and dbt exams for week 63. | Add the AWS certificate to your profile. Rate review: move to $40–45/hr if win rate holds.
58 | 2027-11-01 | 7 | Capstone design | 20 |  | Not started |  | P14 | Architecture decision records, requirements writing. | P14: requirements, architecture diagram, Terraform for all AWS and Snowflake environments. | 3–5 proposals. Keep active clients happy first.
59 | 2027-11-08 | 7 | Capstone build I | 20 |  | Not started |  | P14 | — | P14: batch ingestion (dlt/Airbyte) plus CDC stream; dbt staging and marts. | 3–5 proposals.
60 | 2027-11-15 | 7 | Capstone build II | 20 |  | Not started |  | P14 | — | P14: Airflow on AWS, GitHub Actions with OIDC deploys, Elementary monitoring, CloudWatch alerts, dashboard. | 3–5 proposals.
61 | 2027-11-22 | 7 | Capstone executive dashboard | 20 |  | Not started |  | P14 | Executive reporting: one-page KPI overview, targets vs actuals, alerts on thresholds, sharing with non-technical users. | P14: Power BI executive dashboard (sales, marketing and operations pages) on the capstone warehouse, with row-level security and scheduled refresh. | 3–5 proposals.
62 | 2027-11-29 | 7 | Capstone delivery | 20 |  | Not started |  | P14 | Recording a clear walkthrough video. | P14 finish: runbook, docs, 5-minute walkthrough video that opens with the executive dashboard, case study. | Make P14 the first item in your portfolio.
63 | 2027-12-06 | 7 | Certification week | 15 |  | Not started |  |  | Final review. | Take SnowPro Core and the dbt Analytics Engineering exam. | Add certifications to your profile.
64 | 2027-12-13 | 7 | Launch & next-stage plan | 15 |  | Not started |  |  | — | Portfolio polish, update every case study with results. Full retrospective. Write the plan for the next stage. | Raise your rate to $45–50/hr for new clients. Set targets for the next stage.
|  |  | Totals | 1225 | 20
Formulas:
Start = Dashboard!$B5+([Week]-1)*7

## Projects
Portfolio Projects
One row per project. Planned weeks and stack come from the roadmap; the yellow columns are yours.
ID | Project | Planned weeks | Stack | Status | Started | Finished | GitHub link | Case study | On Upwork portfolio | Key result (with a number) | Done when
P1 | Sakila: from MySQL to a star schema | 3–6 | MySQL, DuckDB, dbt-duckdb, Metabase (Docker) | In progress | 2026-10-12 |  | github.com/your-user/sakila-analytics | No | No | Example: dashboard answers 5 questions; 42 dbt tests passing | dbt build passes with tests on every primary key; dashboard answers 5 business questions
P2 | Olist marketplace analytics on Snowflake | 7–11, 16 | Snowflake, dbt Core, GitHub Actions, SQLFluff, Metabase | Not started |  |  |  | No | No |  | CI runs on every pull request; dashboard shows revenue, AOV, delivery SLA, seller scores
P3 | GA4 marketing analytics on BigQuery (Google Cloud) | 12–15 | BigQuery, dbt-bigquery, Looker Studio, Docker, Cloud Run jobs, Cloud Scheduler, Secret Manager | Not started |  |  |  | No | No |  | Funnel from session to purchase by channel; dbt runs daily in Cloud Run without your laptop; documented bytes-scanned savings
P4 | Sales analytics dashboard in Power BI | 18–21 | Power BI Desktop and Service, DAX, Snowflake connector, row-level security, scheduled refresh | Not started |  |  |  | No | No |  | A non-technical person can answer 5 business questions from it in under a minute; refresh runs on schedule
P5 | Marketing performance dashboard | 22–23 | BigQuery, dbt, Looker Studio, Power BI | Not started |  |  |  | No | No |  | Spend, sessions and revenue reconcile by channel and day; dashboard ranks campaigns by ROAS
P6 | SaaS revenue metrics (MRR, churn, LTV) | 27–28 | Python, dlt, Airbyte, Snowflake, dbt, Airflow, Power BI | Not started |  |  |  | No | No |  | MRR bridge (new, expansion, contraction, churn) reconciles to raw invoices
P7 | NYC Taxi pipeline deployed on AWS | 32–33 | Terraform, S3, SQS + Snowpipe, Snowflake, dbt incremental, Airflow on ECS Fargate/EC2 (MWAA demo), CloudWatch, SNS alerts | Not started |  |  |  | No | No |  | terraform apply creates everything from scratch; reruns are idempotent; a failed run sends an alert
P8 | MySQL to Snowflake migration | 34–35 | Amazon RDS for MySQL, Airbyte or dlt, Snowflake, Python reconciliation scripts | Not started |  |  |  | No | No |  | Row counts and checksums match for every table; runbook tested once end to end
P9 | Real-time orders with CDC | 37–40 | MySQL binlog, Debezium, Kafka/Redpanda, Snowflake Kafka connector, Dynamic Tables, dbt | Not started |  |  |  | No | No |  | Inserts, updates and deletes appear in Snowflake within target latency; replay after failure works
P10 | Serverless lakehouse on AWS (Glue, Athena, Iceberg) | 42–44 | PySpark, AWS Glue jobs and Data Catalog, S3, Apache Iceberg, Athena, Step Functions or Airflow, Terraform | Not started |  |  |  | No | No |  | Glue jobs run on the full dataset; Athena queries use partition pruning; costs documented
P11 | Warehouse cost audit | 47–48 | Snowflake query history, query profile, resource monitors, dbt | Not started |  |  |  | No | No |  | Measured cost reduction with evidence for each change
P12 | E-commerce analytics starter kit | 50–51 | Shopify API, dlt, Snowflake or BigQuery, dbt template, Power BI template (.pbit), Looker Studio template | Not started |  |  |  | No | No |  | A new store can be set up from the template in one day
P13 | Redshift on AWS | 53 | Redshift Serverless, Redshift Spectrum, S3, dbt-redshift, Terraform | Not started |  |  |  | No | No |  | dbt build passes on Redshift with the same tests as P2
P14 | Capstone: modern data platform on AWS | 58–62 | Terraform, AWS (S3, ECS/MWAA, Secrets Manager, CloudWatch), Snowflake, dlt/Airbyte, Debezium/Kafka, dbt, Airflow, GitHub Actions with OIDC, Elementary, Power BI | Not started |  |  |  | No | No |  | Someone else could run it from your README; video explains business value in plain words

## Skills
Skills Self-Assessment
Rate yourself 1–5 at the end of each quarter (1 = never used, 3 = can do with docs, 5 = could teach it).
Area | Skill | Target | Check 1 (wk 16) | Check 2 (wk 32) | Check 3 (wk 48) | Check 4 (wk 64) | Status | Evidence (project / link)
SQL | Window functions & analytical patterns | 5 |  |  |  |  | Not rated
SQL | Query performance in columnar warehouses | 4 |  |  |  |  | Not rated
Modeling | Kimball dimensional modeling | 5 |  |  |  |  | Not rated
Modeling | SCD & snapshots | 4 |  |  |  |  | Not rated
Python | pandas / polars | 4 |  |  |  |  | Not rated
Python | API extraction, pagination, retries | 4 |  |  |  |  | Not rated
Python | Testing with pytest | 3 |  |  |  |  | Not rated
dbt | Models, sources, refs, materializations | 5 |  |  |  |  | Not rated
dbt | Incremental models | 5 |  |  |  |  | Not rated
dbt | Macros & Jinja | 4 |  |  |  |  | Not rated
dbt | Tests, unit tests, contracts | 5 |  |  |  |  | Not rated
dbt | CI/CD with GitHub Actions | 4 |  |  |  |  | Not rated
Warehouse | Snowflake (main) | 5 |  |  |  |  | Not rated
Warehouse | BigQuery (second) | 4 |  |  |  |  | Not rated
Warehouse | Redshift (working level) | 3 |  |  |  |  | Not rated
Warehouse | Cost & performance optimization | 4 |  |  |  |  | Not rated
Ingestion | Airbyte | 4 |  |  |  |  | Not rated
Ingestion | dlt | 4 |  |  |  |  | Not rated
Ingestion | Snowpipe / COPY INTO / stages | 4 |  |  |  |  | Not rated
Orchestration | Airflow | 4 |  |  |  |  | Not rated
Streaming | Kafka fundamentals | 3 |  |  |  |  | Not rated
Streaming | CDC with Debezium | 4 |  |  |  |  | Not rated
Streaming | Snowflake streaming & Dynamic Tables | 3 |  |  |  |  | Not rated
Big data | PySpark | 3 |  |  |  |  | Not rated
Big data | Iceberg / Delta Lake | 3 |  |  |  |  | Not rated
Quality | Elementary / observability | 3 |  |  |  |  | Not rated
Infra | Docker & Linux (existing strength) | 4 |  |  |  |  | Not rated
Consulting | Scoping, estimates, proposals | 4 |  |  |  |  | Not rated
Consulting | Writing case studies | 4 |  |  |  |  | Not rated
Cloud (AWS) | IAM, S3, VPC basics, Secrets Manager | 5 |  |  |  |  | Not rated
Cloud (AWS) | Compute for pipelines: Lambda, ECS Fargate, MWAA | 4 |  |  |  |  | Not rated
Cloud (AWS) | Glue, Athena, Lake Formation | 4 |  |  |  |  | Not rated
Cloud (AWS) | CloudWatch, SNS, cost & budgets | 4 |  |  |  |  | Not rated
Cloud (GCP) | Service accounts, GCS, Cloud Run, Scheduler | 3 |  |  |  |  | Not rated
Infra | Terraform (AWS + Snowflake providers) | 4 |  |  |  |  | Not rated
Infra | CI/CD with GitHub Actions OIDC | 3 |  |  |  |  | Not rated
BI | Power BI data modeling & Power Query | 5 |  |  |  |  | Not rated
BI | DAX (measures, time intelligence) | 4 |  |  |  |  | Not rated
BI | Power BI Service: RLS, refresh, sharing | 4 |  |  |  |  | Not rated
BI | Looker Studio | 4 |  |  |  |  | Not rated
BI | Metabase (self-hosted) | 3 |  |  |  |  | Not rated
BI | Dashboard design & storytelling | 5 |  |  |  |  | Not rated
BI | Metric definitions & semantic layer | 3 |  |  |  |  | Not rated
Business | Sales & e-commerce KPIs | 5 |  |  |  |  | Not rated
Business | Marketing analytics (ROAS, CAC, attribution) | 4 |  |  |  |  | Not rated
Business | SaaS metrics (MRR, churn, cohorts) | 4 |  |  |  |  | Not rated

## Upwork Pipeline
Upwork Pipeline
One row per proposal. Row 5 is an example of the format; start your entries from row 6.
Date sent | Job title | Client country | Category | Type | Connects | Rate / budget ($) | Template used | Viewed | Interview | Hired | Contract value ($) | Notes
2026-12-12 | Build dbt models on Snowflake for Shopify data | USA | dbt / Snowflake | Fixed | 16 | 250 | dbt fix | Yes | Yes | No | 0 | Example row. Client chose a cheaper bid.

## Monthly Review
Monthly Review
Month columns are calculated from the start date. Proposals and hours are pulled automatically; income and reflections are yours.
Month # | Month starting | Weeks done | Hours logged | Proposals | Hires | Niche income ($) | Total freelance income ($) | Current rate ($/hr) | What worked | What to change next month
1 | 2026-09-01 | 1 | 20 | 0 | 0 | 0 | 900 | 20 | Example: finished P1 on time; DBA contract covered costs.
2 | 2026-10-01 | 0 | 0 | 0 | 0
3 | 2026-11-01 | 0 | 0 | 0 | 0
4 | 2026-12-01 | 0 | 0 | 0 | 0
5 | 2027-01-01 | 0 | 0 | 0 | 0
6 | 2027-02-01 | 0 | 0 | 0 | 0
7 | 2027-03-01 | 0 | 0 | 0 | 0
8 | 2027-04-01 | 0 | 0 | 0 | 0
9 | 2027-05-01 | 0 | 0 | 0 | 0
10 | 2027-06-01 | 0 | 0 | 0 | 0
11 | 2027-07-01 | 0 | 0 | 0 | 0
12 | 2027-08-01 | 0 | 0 | 0 | 0
13 | 2027-09-01 | 0 | 0 | 0 | 0
14 | 2027-10-01 | 0 | 0 | 0 | 0
15 | 2027-11-01 | 0 | 0 | 0 | 0
16 | 2027-12-01 | 0 | 0 | 0 | 0
Total |  | 1 | 20 | 0 | 0 | 0 | 900
Note: the Dashboard reads the last month where column H has a number.
Formulas:
Month starting = DATE(YEAR(Dashboard!$B5),MONTH(Dashboard!$B5)+[Month #]-1,1)